## Sublot 01 – North Lot
| Temporary Structure Scenarios |  |  | Legend
| Up to 1000 m² | 4 months of construction |  | PRO | Work Delivery and Acceptance
| From 1000 to 3000 m² | 6 months of construction |  | PO | Pre-Construction Period – Approvals
| Above 3000 m² | 8 months of construction |  | EP | Temporary Structure Assembly / Disassembly
| No-Migration Scenarios |  |  | O | Construction Period **Numbers indicate work teams
| Up to 1000 m² | 6 months of construction |  | EN | Entrega e Aceite de Obra
| From 1000 to 3000 m² | 8 months of construction
| Above 3000 m² | 10 months of construction
[11 empty] | FIRST YEAR | [11 empty] | SECOND YEAR | [11 empty] | THIRD YEAR | [11 empty] | FOURTH YEAR
ID | INEP Code | School Unit | Municipality | Sub-lot | Typology | Built Area | Built Area (with 10% increase) | Relocation Scenario | Construction Year | Construction Period (month) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48
63 | 31062472 | EE OLEGARIO MACIEL | JANUÁRIA | North | D1 | 3271.26 | 3598.386 | Internal | 1 | 10 | FIRST YEAR 1: PRO; FIRST YEAR 2: PRO; FIRST YEAR 3: PRO; FIRST YEAR 4: PO; FIRST YEAR 5: O1; FIRST YEAR 6: O1; FIRST YEAR 7: O1; FIRST YEAR 8: O1; FIRST YEAR 9: O1; FIRST YEAR 10: O1; FIRST YEAR 11: O1; FIRST YEAR 12: O1; SECOND YEAR 13: O1; SECOND YEAR 14: O1; SECOND YEAR 15: EN
69 | 31062642 | EE MONSENHOR FLORISVAL MONTALVAO | JANUÁRIA | North | A | 2937 | 3230.7 | Internal | 1 | 10 | FIRST YEAR 1: PRO; FIRST YEAR 2: PRO; FIRST YEAR 3: PRO; FIRST YEAR 4: PO; FIRST YEAR 5: O2; FIRST YEAR 6: O2; FIRST YEAR 7: O2; FIRST YEAR 8: O2; FIRST YEAR 9: O2; FIRST YEAR 10: O2; FIRST YEAR 11: O2; FIRST YEAR 12: O2; SECOND YEAR 13: O2; SECOND YEAR 14: O2; SECOND YEAR 15: EN
76 | 31081418 | EE AUGUSTA VALLE | MONTES CLAROS | North | A | 3188.4024 | 3507.2427 | Internal | 1 | 10 | FIRST YEAR 1: PRO; FIRST YEAR 2: PRO; FIRST YEAR 3: PRO; FIRST YEAR 4: PO; FIRST YEAR 5: O3; FIRST YEAR 6: O3; FIRST YEAR 7: O3; FIRST YEAR 8: O3; FIRST YEAR 9: O3; FIRST YEAR 10: O3; FIRST YEAR 11: O3; FIRST YEAR 12: O3; SECOND YEAR 13: O3; SECOND YEAR 14: O3; SECOND YEAR 15: EN
77 | 31081396 | EE DOUTOR CARLOS ALBUQUERQUE | MONTES CLAROS | North | A | 3165.9219 | 3482.514 | Internal | 1 | 10 | FIRST YEAR 1: PRO; FIRST YEAR 2: PRO; FIRST YEAR 3: PRO; FIRST YEAR 4: PO; FIRST YEAR 5: O4; FIRST YEAR 6: O4; FIRST YEAR 7: O4; FIRST YEAR 8: O4; FIRST YEAR 9: O4; FIRST YEAR 10: O4; FIRST YEAR 11: O4; FIRST YEAR 12: O4; SECOND YEAR 13: O4; SECOND YEAR 14: O4; SECOND YEAR 15: EN
91 | 31205664 | EE LEVI DURAES PERES | MONTES CLAROS | North | D | 4241 | 4665.1 | Internal | 1 | 10 | FIRST YEAR 1: PRO; FIRST YEAR 2: PRO; FIRST YEAR 3: PRO; FIRST YEAR 4: PO; FIRST YEAR 5: O5; FIRST YEAR 6: O5; FIRST YEAR 7: O5; FIRST YEAR 8: O5; FIRST YEAR 9: O5; FIRST YEAR 10: O5; FIRST YEAR 11: O5; FIRST YEAR 12: O5; SECOND YEAR 13: O5; SECOND YEAR 14: O5; SECOND YEAR 15: EN
97 | 31081540 | EE PROFESSORA DILMA QUADROS | MONTES CLAROS | North | B | 2184.3 | 2402.73 | Internal | 1 | 8 | FIRST YEAR 1: PRO; FIRST YEAR 2: PRO; FIRST YEAR 3: PRO; FIRST YEAR 4: PO; FIRST YEAR 5: O6; FIRST YEAR 6: O6; FIRST YEAR 7: O6; FIRST YEAR 8: O6; FIRST YEAR 9: O6; FIRST YEAR 10: O6; FIRST YEAR 11: O6; FIRST YEAR 12: O6; SECOND YEAR 13: EN
101 | 31081434 | EE MARIA DA CONCEICAO RODRIGUES AVELAR | MONTES CLAROS | North | D | 2919 | 3210.9 | Internal | 1 | 10 | FIRST YEAR 1: PRO; FIRST YEAR 2: PRO; FIRST YEAR 3: PRO; FIRST YEAR 4: PO; FIRST YEAR 5: O7; FIRST YEAR 6: O7; FIRST YEAR 7: O7; FIRST YEAR 8: O7; FIRST YEAR 9: O7; FIRST YEAR 10: O7; FIRST YEAR 11: O7; FIRST YEAR 12: O7; SECOND YEAR 13: O7; SECOND YEAR 14: O7; SECOND YEAR 15: EN
84 | 31081809 | EE PROFESSORA DULCE SARMENTO | MONTES CLAROS | North | D | 1960.32 | 2156.352 | Internal | 1 | 8 | FIRST YEAR 1: PRO; FIRST YEAR 2: PRO; FIRST YEAR 3: PRO; FIRST YEAR 4: PO; FIRST YEAR 5: O8; FIRST YEAR 6: O8; FIRST YEAR 7: O8; FIRST YEAR 8: O8; FIRST YEAR 9: O8; FIRST YEAR 10: O8; FIRST YEAR 11: O8; FIRST YEAR 12: O8; SECOND YEAR 13: EN
78 | 31081591 | EE ELOY PEREIRA | MONTES CLAROS | North | B | 2127 | 2339.7 | Internal | 1 | 8 | FIRST YEAR 1: PRO; FIRST YEAR 2: PRO; FIRST YEAR 3: PRO; FIRST YEAR 4: PO; FIRST YEAR 5: O9; FIRST YEAR 6: O9; FIRST YEAR 7: O9; FIRST YEAR 8: O9; FIRST YEAR 9: O9; FIRST YEAR 10: O9; FIRST YEAR 11: O9; FIRST YEAR 12: O9; SECOND YEAR 13: EN
95 | 31081264 | EE PROFESSOR PLINIO RIBEIRO | MONTES CLAROS | North | B | 8006.1 | 8806.71 | Internal | 1 | 10 | FIRST YEAR 1: PRO; FIRST YEAR 2: PRO; FIRST YEAR 3: PRO; FIRST YEAR 4: PO; FIRST YEAR 5: O10; FIRST YEAR 6: O10; FIRST YEAR 7: O10; FIRST YEAR 8: O10; FIRST YEAR 9: O10; FIRST YEAR 10: O10; FIRST YEAR 11: O10; FIRST YEAR 12: O10; SECOND YEAR 13: O10; SECOND YEAR 14: O10; SECOND YEAR 15: EN
98 | 31081795 | EE PROFESSOR ALCIDES DE CARVALHO | MONTES CLAROS | North | A | 5157 | 5672.7 | Internal | 1 | 10 | FIRST YEAR 1: PRO; FIRST YEAR 2: PRO; FIRST YEAR 3: PRO; FIRST YEAR 4: PO; FIRST YEAR 5: O11; FIRST YEAR 6: O11; FIRST YEAR 7: O11; FIRST YEAR 8: O11; FIRST YEAR 9: O11; FIRST YEAR 10: O11; FIRST YEAR 11: O11; FIRST YEAR 12: O11; SECOND YEAR 13: O11; SECOND YEAR 14: O11; SECOND YEAR 15: EN
88 | 31081400 | EE ARMÊNIO VELOSO | MONTES CLAROS | North | B | 2116.74 | 2328.414 | Internal | 1 | 8 | FIRST YEAR 1: PRO; FIRST YEAR 2: PRO; FIRST YEAR 3: PRO; FIRST YEAR 4: PO; FIRST YEAR 5: O12; FIRST YEAR 6: O12; FIRST YEAR 7: O12; FIRST YEAR 8: O12; FIRST YEAR 9: O12; FIRST YEAR 10: O12; FIRST YEAR 11: O12; FIRST YEAR 12: O12; SECOND YEAR 13: EN
67 | 31063096 | EE DONA ALICE MENDONCA | SÃO FRANCISCO | North | B | 1901.3 | 2091.43 | Internal | 1 | 8 | FIRST YEAR 1: PRO; FIRST YEAR 2: PRO; FIRST YEAR 3: PRO; FIRST YEAR 4: PO; FIRST YEAR 5: O13; FIRST YEAR 6: O13; FIRST YEAR 7: O13; FIRST YEAR 8: O13; FIRST YEAR 9: O13; FIRST YEAR 10: O13; FIRST YEAR 11: O13; FIRST YEAR 12: O13; SECOND YEAR 13: EN
79 | 31079383 | EE ZINHA MEIRA | BOCAIÚVA | North | A | 3487.04 | 3835.744 | Internal | 1 | 10 | FIRST YEAR 1: PRO; FIRST YEAR 2: PRO; FIRST YEAR 3: PRO; FIRST YEAR 4: PO; FIRST YEAR 5: O14; FIRST YEAR 6: O14; FIRST YEAR 7: O14; FIRST YEAR 8: O14; FIRST YEAR 9: O14; FIRST YEAR 10: O14; FIRST YEAR 11: O14; FIRST YEAR 12: O14; SECOND YEAR 13: O14; SECOND YEAR 14: O14; SECOND YEAR 15: EN
81 | 31079448 | EE PROFESSOR GASTAO VALLE | BOCAIÚVA | North | D | 3926 | 4318.6 | Internal | 1 | 10 | FIRST YEAR 1: PRO; FIRST YEAR 2: PRO; FIRST YEAR 3: PRO; FIRST YEAR 4: PO; FIRST YEAR 5: O15; FIRST YEAR 6: O15; FIRST YEAR 7: O15; FIRST YEAR 8: O15; FIRST YEAR 9: O15; FIRST YEAR 10: O15; FIRST YEAR 11: O15; FIRST YEAR 12: O15; SECOND YEAR 13: O15; SECOND YEAR 14: O15; SECOND YEAR 15: EN
87 | 31079863 | EE BENICIO PRATES | CORAÇÃO DE JESUS | North | A | 2251.0605 | 2476.1665 | Internal | 1 | 8 | FIRST YEAR 1: PRO; FIRST YEAR 2: PRO; FIRST YEAR 3: PRO; FIRST YEAR 4: PO; FIRST YEAR 5: O16; FIRST YEAR 6: O16; FIRST YEAR 7: O16; FIRST YEAR 8: O16; FIRST YEAR 9: O16; FIRST YEAR 10: O16; FIRST YEAR 11: O16; FIRST YEAR 12: O16; SECOND YEAR 13: EN
90 | 31079944 | EE CORONEL LUIS PIRES DE MINAS | CORAÇÃO DE JESUS | North | A | 2529 | 2781.9 | Internal | 1 | 8 | FIRST YEAR 1: PRO; FIRST YEAR 2: PRO; FIRST YEAR 3: PRO; FIRST YEAR 4: PO; FIRST YEAR 5: O17; FIRST YEAR 6: O17; FIRST YEAR 7: O17; FIRST YEAR 8: O17; FIRST YEAR 9: O17; FIRST YEAR 10: O17; FIRST YEAR 11: O17; FIRST YEAR 12: O17; SECOND YEAR 13: EN
100 | 31239241 | EE SAO JOSE | CORAÇÃO DE JESUS | North | A | 1508.45 | 1659.295 | Internal | 1 | 8 | FIRST YEAR 1: PRO; FIRST YEAR 2: PRO; FIRST YEAR 3: PRO; FIRST YEAR 4: PO; FIRST YEAR 5: O18; FIRST YEAR 6: O18; FIRST YEAR 7: O18; FIRST YEAR 8: O18; FIRST YEAR 9: O18; FIRST YEAR 10: O18; FIRST YEAR 11: O18; FIRST YEAR 12: O18; SECOND YEAR 13: EN
85 | 31082678 | EE GUIMARAES ROSA | LONTRA | North | B | 2574.59 | 2832.049 | Internal | 1 | 8 | FIRST YEAR 1: PRO; FIRST YEAR 2: PRO; FIRST YEAR 3: PRO; FIRST YEAR 4: PO; FIRST YEAR 5: O19; FIRST YEAR 6: O19; FIRST YEAR 7: O19; FIRST YEAR 8: O19; FIRST YEAR 9: O19; FIRST YEAR 10: O19; FIRST YEAR 11: O19; FIRST YEAR 12: O19; SECOND YEAR 13: EN
93 | 31080900 | EE PROFESSORA MARIA MACHADO | MIRABELA | North | B | 2939 | 3232.9 | Internal | 1 | 10 | FIRST YEAR 1: PRO; FIRST YEAR 2: PRO; FIRST YEAR 3: PRO; FIRST YEAR 4: PO; FIRST YEAR 5: O20; FIRST YEAR 6: O20; FIRST YEAR 7: O20; FIRST YEAR 8: O20; FIRST YEAR 9: O20; FIRST YEAR 10: O20; FIRST YEAR 11: O20; FIRST YEAR 12: O20; SECOND YEAR 13: O20; SECOND YEAR 14: O20; SECOND YEAR 15: EN
64 | 31240222 | EE BRASILIANO BRAZ | SÃO FRANCISCO | North | A | 4980.72 | 5478.792 | Internal | 2 | 10 | FIRST YEAR 9: PRO; FIRST YEAR 10: PRO; FIRST YEAR 11: PRO; FIRST YEAR 12: PO; SECOND YEAR 13: O16; SECOND YEAR 14: O16; SECOND YEAR 15: O16; SECOND YEAR 16: O16; SECOND YEAR 17: O16; SECOND YEAR 18: O16; SECOND YEAR 19: O16; SECOND YEAR 20: O16; SECOND YEAR 21: O16; SECOND YEAR 22: O16; SECOND YEAR 23: EN
83 | 31081485 | EE DELFINO MAGALHAES | MONTES CLAROS | North | A | 2752.35 | 3027.585 | Internal | 2 | 10 | FIRST YEAR 9: PRO; FIRST YEAR 10: PRO; FIRST YEAR 11: PRO; FIRST YEAR 12: PO; SECOND YEAR 13: O17; SECOND YEAR 14: O17; SECOND YEAR 15: O17; SECOND YEAR 16: O17; SECOND YEAR 17: O17; SECOND YEAR 18: O17; SECOND YEAR 19: O17; SECOND YEAR 20: O17; SECOND YEAR 21: O17; SECOND YEAR 22: O17; SECOND YEAR 23: EN
82 | 31080918 | EE FRANCISCO ANDRADE | PATIS | North | B | 2038 | 2241.8 | Internal | 2 | 8 | FIRST YEAR 11: PRO; FIRST YEAR 12: PRO; SECOND YEAR 13: PRO; SECOND YEAR 14: PO; SECOND YEAR 15: O3; SECOND YEAR 16: O3; SECOND YEAR 17: O3; SECOND YEAR 18: O3; SECOND YEAR 19: O3; SECOND YEAR 20: O3; SECOND YEAR 21: O3; SECOND YEAR 22: O3; SECOND YEAR 23: EN
89 | 31082732 | EE MENDES DE OLIVEIRA | SÃO JOÃO DO PARAÍSO | North | A1 | 1879 | 2066.9 | Internal | 2 | 8 | FIRST YEAR 11: PRO; FIRST YEAR 12: PRO; SECOND YEAR 13: PRO; SECOND YEAR 14: PO; SECOND YEAR 15: O4; SECOND YEAR 16: O4; SECOND YEAR 17: O4; SECOND YEAR 18: O4; SECOND YEAR 19: O4; SECOND YEAR 20: O4; SECOND YEAR 21: O4; SECOND YEAR 22: O4; SECOND YEAR 23: EN
73 | 31063452 | EE MARIA BATISTA CAVALCANTI | UBAÍ | North | A | 2313.1031 | 2544.4134 | Internal | 2 | 8 | FIRST YEAR 11: PRO; FIRST YEAR 12: PRO; SECOND YEAR 13: PRO; SECOND YEAR 14: PO; SECOND YEAR 15: O5; SECOND YEAR 16: O5; SECOND YEAR 17: O5; SECOND YEAR 18: O5; SECOND YEAR 19: O5; SECOND YEAR 20: O5; SECOND YEAR 21: O5; SECOND YEAR 22: O5; SECOND YEAR 23: EN
96 | 31079600 | EE SANTANA | BRASÍLIA DE MINAS | North | B | 2307 | 2537.7 | Internal | 2 | 8 | FIRST YEAR 9: PRO; FIRST YEAR 10: PRO; FIRST YEAR 11: PRO; FIRST YEAR 12: PO; SECOND YEAR 13: O6; SECOND YEAR 14: O6; SECOND YEAR 15: O6; SECOND YEAR 16: O6; SECOND YEAR 17: O6; SECOND YEAR 18: O6; SECOND YEAR 19: O6; SECOND YEAR 20: O6; SECOND YEAR 21: EN
75 | 31080349 | EE TIBURTINO PENA | FRANCISCO SÁ | North | D | 3084.16 | 3392.576 | Internal | 2 | 10 | FIRST YEAR 9: PRO; FIRST YEAR 10: PRO; FIRST YEAR 11: PRO; FIRST YEAR 12: PO; SECOND YEAR 13: O18; SECOND YEAR 14: O18; SECOND YEAR 15: O18; SECOND YEAR 16: O18; SECOND YEAR 17: O18; SECOND YEAR 18: O18; SECOND YEAR 19: O18; SECOND YEAR 20: O18; SECOND YEAR 21: O18; SECOND YEAR 22: O18; SECOND YEAR 23: EN
65 | 31062308 | EE PROFESSOR JOSEFINO BARBOSA | ITACARAMBI | North | B | 4014 | 4415.4 | Internal | 2 | 10 | FIRST YEAR 9: PRO; FIRST YEAR 10: PRO; FIRST YEAR 11: PRO; FIRST YEAR 12: PO; SECOND YEAR 13: O8; SECOND YEAR 14: O8; SECOND YEAR 15: O8; SECOND YEAR 16: O8; SECOND YEAR 17: O8; SECOND YEAR 18: O8; SECOND YEAR 19: O8; SECOND YEAR 20: O8; SECOND YEAR 21: O8; SECOND YEAR 22: O8; SECOND YEAR 23: EN
66 | 31062995 | EE ANTONIO ORTIGA | JUVENÍLIA | North | D1 | 3866.62 | 4253.282 | Internal | 2 | 10 | FIRST YEAR 9: PRO; FIRST YEAR 10: PRO; FIRST YEAR 11: PRO; FIRST YEAR 12: PO; SECOND YEAR 13: O9; SECOND YEAR 14: O9; SECOND YEAR 15: O9; SECOND YEAR 16: O9; SECOND YEAR 17: O9; SECOND YEAR 18: O9; SECOND YEAR 19: O9; SECOND YEAR 20: O9; SECOND YEAR 21: O9; SECOND YEAR 22: O9; SECOND YEAR 23: EN
74 | 31246280 | EE MARIA ROSA NUNES (JANUÁRIA) | JANUÁRIA | North | A1 | 1415 | 1556.5 | Internal | 2 | 8 | FIRST YEAR 11: PRO; FIRST YEAR 12: PRO; SECOND YEAR 13: PRO; SECOND YEAR 14: PO; SECOND YEAR 15: O10; SECOND YEAR 16: O10; SECOND YEAR 17: O10; SECOND YEAR 18: O10; SECOND YEAR 19: O10; SECOND YEAR 20: O10; SECOND YEAR 21: O10; SECOND YEAR 22: O10; SECOND YEAR 23: EN
74A | 31246280 | EE MARIA ROSA NUNES ANEXO (SÃO FRANCISCO) | SÃO FRANCISCO | North | A1 | 1265.26 | 1391.786 | Internal | 2 | 8 | FIRST YEAR 11: PRO; FIRST YEAR 12: PRO; SECOND YEAR 13: PRO; SECOND YEAR 14: PO; SECOND YEAR 15: O11; SECOND YEAR 16: O11; SECOND YEAR 17: O11; SECOND YEAR 18: O11; SECOND YEAR 19: O11; SECOND YEAR 20: O11; SECOND YEAR 21: O11; SECOND YEAR 22: O11; SECOND YEAR 23: EN
86 | 31081311 | EE BENJAMIN VERSIANI DOS ANJOS | MONTES CLAROS | North | B | 2090 | 2299 | Internal | 2 | 8 | FIRST YEAR 9: PRO; FIRST YEAR 10: PRO; FIRST YEAR 11: PRO; FIRST YEAR 12: PO; SECOND YEAR 13: O12; SECOND YEAR 14: O12; SECOND YEAR 15: O12; SECOND YEAR 16: O12; SECOND YEAR 17: O12; SECOND YEAR 18: O12; SECOND YEAR 19: O12; SECOND YEAR 20: O12; SECOND YEAR 21: EN
80 | 31081761 | EE ANTONIO CANELA | MONTES CLAROS | North | D | 2734 | 3007.4 | Internal | 2 | 10 | FIRST YEAR 9: PRO; FIRST YEAR 10: PRO; FIRST YEAR 11: PRO; FIRST YEAR 12: PO; SECOND YEAR 13: O13; SECOND YEAR 14: O13; SECOND YEAR 15: O13; SECOND YEAR 16: O13; SECOND YEAR 17: O13; SECOND YEAR 18: O13; SECOND YEAR 19: O13; SECOND YEAR 20: O13; SECOND YEAR 21: O13; SECOND YEAR 22: O13; SECOND YEAR 23: EN
94 | 31081507 | EE PROFESSOR HAMILTON LOPES | MONTES CLAROS | North | B | 2592 | 2851.2 | Internal | 2 | 8 | FIRST YEAR 11: PRO; FIRST YEAR 12: PRO; SECOND YEAR 13: PRO; SECOND YEAR 14: PO; SECOND YEAR 15: O14; SECOND YEAR 16: O14; SECOND YEAR 17: O14; SECOND YEAR 18: O14; SECOND YEAR 19: O14; SECOND YEAR 20: O14; SECOND YEAR 21: O14; SECOND YEAR 22: O14; SECOND YEAR 23: EN

## Sublot 02 – RMBH Lot
| Temporary Structure Scenarios |  |  | Legend
| Up to 1000 m² | 4 months of construction |  | PRO | Work Delivery and Acceptance
| From 1000 to 3000 m² | 6 months of construction |  | PO | Pre-Construction Period – Approvals
| Above 3000 m² | 8 months of construction |  | EP | Temporary Structure Assembly / Disassembly
| No-Migration Scenarios |  |  | O | Construction Period **Numbers indicate work teams
| Up to 1000 m² | 6 months of construction |  | EN | Entrega e Aceite de Obra
| From 1000 to 3000 m² | 8 months of construction
| Above 3000 m² | 10 months of construction
[11 empty] | FIRST YEAR | [11 empty] | SECOND YEAR | [11 empty] | THIRD YEAR | [11 empty] | FOURTH YEAR
ID | INEP Code | School Unit | Municipality | Sub-lot | Typology | Built Area | Built Area (with 10% increase) | Relocation Scenario | Construction Year | Construction Period (month) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48
31 | 31007862 | EE JOÃO PAULO I | BETIM | RMBH | B1 | 2548.82 | 2803.702 | Shared Temporary Structure | 1 | 6 | FIRST YEAR 1: PRO; FIRST YEAR 2: PRO; FIRST YEAR 3: PRO; FIRST YEAR 4: PO; FIRST YEAR 5: EP; FIRST YEAR 6: O1; FIRST YEAR 7: O1; FIRST YEAR 8: O1; FIRST YEAR 9: O1; FIRST YEAR 10: O1; FIRST YEAR 11: O1; FIRST YEAR 12: EN; SECOND YEAR 13: EP
62 | 31010812 | EE RENY DE SOUZA LIMA | SANTA LUZIA | RMBH | A1 | 1784.89 | 1963.379 | Shared Temporary Structure | 1 | 6 | FIRST YEAR 1: PRO; FIRST YEAR 2: PRO; FIRST YEAR 3: PRO; FIRST YEAR 4: PO; FIRST YEAR 5: EP; FIRST YEAR 6: O2; FIRST YEAR 7: O2; FIRST YEAR 8: O2; FIRST YEAR 9: O2; FIRST YEAR 10: O2; FIRST YEAR 11: O2; FIRST YEAR 12: EN; SECOND YEAR 13: EP
14 | 31010456 | EE JOSÉ LUIZ GONZAGA FERREIRA | SABARÁ | RMBH | A1 | 1507.85 | 1658.635 | Shared Temporary Structure | 1 | 6 | FIRST YEAR 1: PRO; FIRST YEAR 2: PRO; FIRST YEAR 3: PRO; FIRST YEAR 4: PO; FIRST YEAR 5: EP; FIRST YEAR 6: O3; FIRST YEAR 7: O3; FIRST YEAR 8: O3; FIRST YEAR 9: O3; FIRST YEAR 10: O3; FIRST YEAR 11: O3; FIRST YEAR 12: EN; SECOND YEAR 13: EP
26 | 31008028 | EE DO BAIRRO SÃO CAETANO | BETIM | RMBH | D | 2845.55 | 3130.105 | Internal | 1 | 10 | FIRST YEAR 1: PRO; FIRST YEAR 2: PRO; FIRST YEAR 3: PRO; FIRST YEAR 4: PO; FIRST YEAR 5: O4; FIRST YEAR 6: O4; FIRST YEAR 7: O4; FIRST YEAR 8: O4; FIRST YEAR 9: O4; FIRST YEAR 10: O4; FIRST YEAR 11: O4; FIRST YEAR 12: O4; SECOND YEAR 13: O4; SECOND YEAR 14: O4; SECOND YEAR 15: EN
13 | 31001317 | EE CORAÇÃO EUCARÍSTICO | BELO HORIZONTE | RMBH | B | 1509.16 | 1660.076 | Internal | 1 | 8 | FIRST YEAR 1: PRO; FIRST YEAR 2: PRO; FIRST YEAR 3: PRO; FIRST YEAR 4: PO; FIRST YEAR 5: O5; FIRST YEAR 6: O5; FIRST YEAR 7: O5; FIRST YEAR 8: O5; FIRST YEAR 9: O5; FIRST YEAR 10: O5; FIRST YEAR 11: O5; FIRST YEAR 12: O5; SECOND YEAR 13: EN
32 | 31000795 | EE MINISTRO ALFREDO VILHENA VALLADÃO | BELO HORIZONTE | RMBH | B | 2618.42 | 2880.262 | Internal | 1 | 8 | FIRST YEAR 1: PRO; FIRST YEAR 2: PRO; FIRST YEAR 3: PRO; FIRST YEAR 4: PO; FIRST YEAR 5: O6; FIRST YEAR 6: O6; FIRST YEAR 7: O6; FIRST YEAR 8: O6; FIRST YEAR 9: O6; FIRST YEAR 10: O6; FIRST YEAR 11: O6; FIRST YEAR 12: O6; SECOND YEAR 13: EN
43 | 31001694 | EE PADRE MATIAS | BELO HORIZONTE | RMBH | D1 | 1914.72 | 2106.192 | Internal | 1 | 8 | FIRST YEAR 1: PRO; FIRST YEAR 2: PRO; FIRST YEAR 3: PRO; FIRST YEAR 4: PO; FIRST YEAR 5: O7; FIRST YEAR 6: O7; FIRST YEAR 7: O7; FIRST YEAR 8: O7; FIRST YEAR 9: O7; FIRST YEAR 10: O7; FIRST YEAR 11: O7; FIRST YEAR 12: O7; SECOND YEAR 13: EN
35 | 31007838 | EE NASCIMENTO NUNES LEAL | BETIM | RMBH | B2 | 1748.42 | 1923.262 | Partial Temporary Structure | 1 | 6 | FIRST YEAR 1: PRO; FIRST YEAR 2: PRO; FIRST YEAR 3: PRO; FIRST YEAR 4: PO; FIRST YEAR 5: EP; FIRST YEAR 6: O8; FIRST YEAR 7: O8; FIRST YEAR 8: O8; FIRST YEAR 9: O8; FIRST YEAR 10: O8; FIRST YEAR 11: O8; FIRST YEAR 12: EN; SECOND YEAR 13: EP
108 | 31010251 | EE SANTO ANTÔNIO | RIO ACIMA | RMBH | A2 | 2613.88 | 2875.268 | Partial Temporary Structure | 1 | 6 | FIRST YEAR 1: PRO; FIRST YEAR 2: PRO; FIRST YEAR 3: PRO; FIRST YEAR 4: PO; FIRST YEAR 5: EP; FIRST YEAR 6: O9; FIRST YEAR 7: O9; FIRST YEAR 8: O9; FIRST YEAR 9: O9; FIRST YEAR 10: O9; FIRST YEAR 11: O9; FIRST YEAR 12: EN; SECOND YEAR 13: EP
58 | 31009679 | EE IMACULADA CONCEIÇÃO | PEDRO LEOPOLDO | RMBH | D1 | 3180.22 | 3498.242 | Dedicated Temporary Structure | 1 | 8 | FIRST YEAR 1: PRO; FIRST YEAR 2: PRO; FIRST YEAR 3: PRO; FIRST YEAR 4: PO; FIRST YEAR 5: EP; FIRST YEAR 6: O10; FIRST YEAR 7: O10; FIRST YEAR 8: O10; FIRST YEAR 9: O10; FIRST YEAR 10: O10; FIRST YEAR 11: O10; FIRST YEAR 12: O10; SECOND YEAR 13: O10; SECOND YEAR 14: EN; SECOND YEAR 15: EP
3 | 31009539 | EE AUGUSTO DE LIMA (NOVA LIMA) | NOVA LIMA | RMBH | B1 | 3839.32 | 4223.252 | Dedicated Temporary Structure | 1 | 8 | FIRST YEAR 1: PRO; FIRST YEAR 2: PRO; FIRST YEAR 3: PRO; FIRST YEAR 4: PO; FIRST YEAR 5: EP; FIRST YEAR 6: O11; FIRST YEAR 7: O11; FIRST YEAR 8: O11; FIRST YEAR 9: O11; FIRST YEAR 10: O11; FIRST YEAR 11: O11; FIRST YEAR 12: O11; SECOND YEAR 13: O11; SECOND YEAR 14: EN; SECOND YEAR 15: EP
36 | 31007951 | EE SENADOR TEOTONIO VILELA | BETIM | RMBH | B | 1897.59 | 2087.349 | Internal | 1 | 8 | FIRST YEAR 1: PRO; FIRST YEAR 2: PRO; FIRST YEAR 3: PRO; FIRST YEAR 4: PO; FIRST YEAR 5: O12; FIRST YEAR 6: O12; FIRST YEAR 7: O12; FIRST YEAR 8: O12; FIRST YEAR 9: O12; FIRST YEAR 10: O12; FIRST YEAR 11: O12; FIRST YEAR 12: O12; SECOND YEAR 13: EN
46 | 31007854 | EE AMELIA SANTANA BARBOSA | BETIM | RMBH | B | 4583.4 | 5041.74 | Internal | 1 | 10 | FIRST YEAR 1: PRO; FIRST YEAR 2: PRO; FIRST YEAR 3: PRO; FIRST YEAR 4: PO; FIRST YEAR 5: O13; FIRST YEAR 6: O13; FIRST YEAR 7: O13; FIRST YEAR 8: O13; FIRST YEAR 9: O13; FIRST YEAR 10: O13; FIRST YEAR 11: O13; FIRST YEAR 12: O13; SECOND YEAR 13: O13; SECOND YEAR 14: O13; SECOND YEAR 15: EN
49 | 31007901 | EE JUSCELINO KUBITSCHEK DE OLIVEIRA | BETIM | RMBH | B1 | 2168.02 | 2384.822 | Internal | 1 | 8 | FIRST YEAR 1: PRO; FIRST YEAR 2: PRO; FIRST YEAR 3: PRO; FIRST YEAR 4: PO; FIRST YEAR 5: O14; FIRST YEAR 6: O14; FIRST YEAR 7: O14; FIRST YEAR 8: O14; FIRST YEAR 9: O14; FIRST YEAR 10: O14; FIRST YEAR 11: O14; FIRST YEAR 12: O14; SECOND YEAR 13: EN
44 | 31000159 | EE MANUEL CASASANTA | BELO HORIZONTE | RMBH | B | 1722.21 | 1894.431 | Internal | 1 | 8 | FIRST YEAR 1: PRO; FIRST YEAR 2: PRO; FIRST YEAR 3: PRO; FIRST YEAR 4: PO; FIRST YEAR 5: O15; FIRST YEAR 6: O15; FIRST YEAR 7: O15; FIRST YEAR 8: O15; FIRST YEAR 9: O15; FIRST YEAR 10: O15; FIRST YEAR 11: O15; FIRST YEAR 12: O15; SECOND YEAR 13: EN
15 | 31000825 | EE ANA DE CARVALHO SILVEIRA | BELO HORIZONTE | RMBH | D | 1536 | 1689.6 | Internal | 1 | 8 | FIRST YEAR 1: PRO; FIRST YEAR 2: PRO; FIRST YEAR 3: PRO; FIRST YEAR 4: PO; FIRST YEAR 5: O16; FIRST YEAR 6: O16; FIRST YEAR 7: O16; FIRST YEAR 8: O16; FIRST YEAR 9: O16; FIRST YEAR 10: O16; FIRST YEAR 11: O16; FIRST YEAR 12: O16; SECOND YEAR 13: EN
6 | 31000493 | EE DEPUTADO ILACIR PEREIRA LIMA | BELO HORIZONTE | RMBH | C | 2731.23 | 3004.353 | Internal | 1 | 10 | FIRST YEAR 1: PRO; FIRST YEAR 2: PRO; FIRST YEAR 3: PRO; FIRST YEAR 4: PO; FIRST YEAR 5: O17; FIRST YEAR 6: O17; FIRST YEAR 7: O17; FIRST YEAR 8: O17; FIRST YEAR 9: O17; FIRST YEAR 10: O17; FIRST YEAR 11: O17; FIRST YEAR 12: O17; SECOND YEAR 13: O17; SECOND YEAR 14: O17; SECOND YEAR 15: EN
111 | 31002071 | EE ISABEL DA SILVA POLCK | BELO HORIZONTE | RMBH | A | 1637.39 | 1801.129 | Internal | 1 | 8 | FIRST YEAR 1: PRO; FIRST YEAR 2: PRO; FIRST YEAR 3: PRO; FIRST YEAR 4: PO; FIRST YEAR 5: O18; FIRST YEAR 6: O18; FIRST YEAR 7: O18; FIRST YEAR 8: O18; FIRST YEAR 9: O18; FIRST YEAR 10: O18; FIRST YEAR 11: O18; FIRST YEAR 12: O18; SECOND YEAR 13: EN
103 | 31000841 | EE DOUTOR AURINO MORAIS | BELO HORIZONTE | RMBH | B | 4106.45 | 4517.095 | Internal | 1 | 10 | FIRST YEAR 1: PRO; FIRST YEAR 2: PRO; FIRST YEAR 3: PRO; FIRST YEAR 4: PO; FIRST YEAR 5: O19; FIRST YEAR 6: O19; FIRST YEAR 7: O19; FIRST YEAR 8: O19; FIRST YEAR 9: O19; FIRST YEAR 10: O19; FIRST YEAR 11: O19; FIRST YEAR 12: O19; SECOND YEAR 13: O19; SECOND YEAR 14: O19; SECOND YEAR 15: EN
4 | 31001783 | EE AUGUSTO DE LIMA (BELO HORIZONTE) | BELO HORIZONTE | RMBH | D1 | 1373 | 1510.3 | Internal | 1 | 8 | FIRST YEAR 1: PRO; FIRST YEAR 2: PRO; FIRST YEAR 3: PRO; FIRST YEAR 4: PO; FIRST YEAR 5: O20; FIRST YEAR 6: O20; FIRST YEAR 7: O20; FIRST YEAR 8: O20; FIRST YEAR 9: O20; FIRST YEAR 10: O20; FIRST YEAR 11: O20; FIRST YEAR 12: O20; SECOND YEAR 13: EN
22 | 31007811 | EE CONSELHEIRO AFONSO PENA | BETIM | RMBH | B1 | 1992 | 2191.2 | Shared Temporary Structure | 2 | 6 | FIRST YEAR 9: PRO; FIRST YEAR 10: PRO; FIRST YEAR 11: PRO; FIRST YEAR 12: PO; SECOND YEAR 13: EP; SECOND YEAR 14: O1; SECOND YEAR 15: O1; SECOND YEAR 16: O1; SECOND YEAR 17: O1; SECOND YEAR 18: O1; SECOND YEAR 19: O1; SECOND YEAR 20: EN; SECOND YEAR 21: EP
17 | 31001261 | EE PROFESSOR LEOPOLDO DE MIRANDA | BELO HORIZONTE | RMBH | B1 | 1068.33 | 1175.163 | Shared Temporary Structure | 2 | 6 | FIRST YEAR 9: PRO; FIRST YEAR 10: PRO; FIRST YEAR 11: PRO; FIRST YEAR 12: PO; SECOND YEAR 13: EP; SECOND YEAR 14: O2; SECOND YEAR 15: O2; SECOND YEAR 16: O2; SECOND YEAR 17: O2; SECOND YEAR 18: O2; SECOND YEAR 19: O2; SECOND YEAR 20: EN; SECOND YEAR 21: EP
107 | 31010618 | EE JOSÉ MARIA BICALHO | SANTA LUZIA | RMBH | A | 2016.28 | 2217.908 | Shared Temporary Structure | 2 | 6 | FIRST YEAR 9: PRO; FIRST YEAR 10: PRO; FIRST YEAR 11: PRO; FIRST YEAR 12: PO; SECOND YEAR 13: EP; SECOND YEAR 14: O3; SECOND YEAR 15: O3; SECOND YEAR 16: O3; SECOND YEAR 17: O3; SECOND YEAR 18: O3; SECOND YEAR 19: O3; SECOND YEAR 20: EN; SECOND YEAR 21: EP
105 | 31010731 | EE LEONINA MOURTHÉ | SANTA LUZIA | RMBH | B | 2346.72 | 2581.392 | Internal | 2 | 8 | FIRST YEAR 11: PRO; FIRST YEAR 12: PRO; SECOND YEAR 13: PRO; SECOND YEAR 14: PO; SECOND YEAR 15: O4; SECOND YEAR 16: O4; SECOND YEAR 17: O4; SECOND YEAR 18: O4; SECOND YEAR 19: O4; SECOND YEAR 20: O4; SECOND YEAR 21: O4; SECOND YEAR 22: O4; SECOND YEAR 23: EN
38 | 31008966 | EE SANTA QUITERIA | ESMERALDAS | RMBH | B | 2187.2 | 2405.92 | Internal | 2 | 8 | FIRST YEAR 9: PRO; FIRST YEAR 10: PRO; FIRST YEAR 11: PRO; FIRST YEAR 12: PO; SECOND YEAR 13: O5; SECOND YEAR 14: O5; SECOND YEAR 15: O5; SECOND YEAR 16: O5; SECOND YEAR 17: O5; SECOND YEAR 18: O5; SECOND YEAR 19: O5; SECOND YEAR 20: O5; SECOND YEAR 21: EN
21 | 31001805 | EE FLAVIO DOS SANTOS | BELO HORIZONTE | RMBH | D | 1821 | 2003.1 | Internal | 2 | 8 | FIRST YEAR 9: PRO; FIRST YEAR 10: PRO; FIRST YEAR 11: PRO; FIRST YEAR 12: PO; SECOND YEAR 13: O6; SECOND YEAR 14: O6; SECOND YEAR 15: O6; SECOND YEAR 16: O6; SECOND YEAR 17: O6; SECOND YEAR 18: O6; SECOND YEAR 19: O6; SECOND YEAR 20: O6; SECOND YEAR 21: EN
29 | 31001201 | EE SILVIANO BRANDÃO | BELO HORIZONTE | RMBH | D | 2266.75 | 2493.425 | Internal | 2 | 8 | FIRST YEAR 9: PRO; FIRST YEAR 10: PRO; FIRST YEAR 11: PRO; FIRST YEAR 12: PO; SECOND YEAR 13: O7; SECOND YEAR 14: O7; SECOND YEAR 15: O7; SECOND YEAR 16: O7; SECOND YEAR 17: O7; SECOND YEAR 18: O7; SECOND YEAR 19: O7; SECOND YEAR 20: O7; SECOND YEAR 21: EN
1 | 31000302 | EE PRESIDENTE DUTRA | BELO HORIZONTE | RMBH | D | 5113 | 5624.3 | Internal | 2 | 10 | FIRST YEAR 8: PRO; FIRST YEAR 9: PRO; FIRST YEAR 10: PRO; FIRST YEAR 11: PO; FIRST YEAR 12: O8; SECOND YEAR 13: O8; SECOND YEAR 14: O8; SECOND YEAR 15: O8; SECOND YEAR 16: O8; SECOND YEAR 17: O8; SECOND YEAR 18: O8; SECOND YEAR 19: O8; SECOND YEAR 20: O8; SECOND YEAR 21: O8; SECOND YEAR 22: EN
7 | 31342459 | EE PROFESSORA ALAIDE LISBOA DE OLIVEIRA | BELO HORIZONTE | RMBH | B | 2250.8428 | 2475.9271 | Internal | 2 | 8 | FIRST YEAR 8: PRO; FIRST YEAR 9: PRO; FIRST YEAR 10: PRO; FIRST YEAR 11: PO; FIRST YEAR 12: O9; SECOND YEAR 13: O9; SECOND YEAR 14: O9; SECOND YEAR 15: O9; SECOND YEAR 16: O9; SECOND YEAR 17: O9; SECOND YEAR 18: O9; SECOND YEAR 19: O9; SECOND YEAR 20: EN
12 | 31001686 | EE WALT DISNEY | BELO HORIZONTE | RMBH | C | 3252.5682 | 3577.825 | Internal | 2 | 10 | FIRST YEAR 10: PRO; FIRST YEAR 11: PRO; FIRST YEAR 12: PRO; SECOND YEAR 13: PO; SECOND YEAR 14: O10; SECOND YEAR 15: O10; SECOND YEAR 16: O10; SECOND YEAR 17: O10; SECOND YEAR 18: O10; SECOND YEAR 19: O10; SECOND YEAR 20: O10; SECOND YEAR 21: O10; SECOND YEAR 22: O10; SECOND YEAR 23: O10; SECOND YEAR 24: EN
42 | 31000639 | EE MAURÍCIO MURGEL | BELO HORIZONTE | RMBH | D | 3921.0476 | 4313.1524 | Internal | 2 | 10 | FIRST YEAR 10: PRO; FIRST YEAR 11: PRO; FIRST YEAR 12: PRO; SECOND YEAR 13: PO; SECOND YEAR 14: O11; SECOND YEAR 15: O11; SECOND YEAR 16: O11; SECOND YEAR 17: O11; SECOND YEAR 18: O11; SECOND YEAR 19: O11; SECOND YEAR 20: O11; SECOND YEAR 21: O11; SECOND YEAR 22: O11; SECOND YEAR 23: O11; SECOND YEAR 24: EN
47 | 31001791 | EE DESEMBARGADOR RODRIGUES CAMPOS | BELO HORIZONTE | RMBH | A | 1932.2 | 2125.42 | Internal | 2 | 8 | FIRST YEAR 9: PRO; FIRST YEAR 10: PRO; FIRST YEAR 11: PRO; FIRST YEAR 12: PO; SECOND YEAR 13: O12; SECOND YEAR 14: O12; SECOND YEAR 15: O12; SECOND YEAR 16: O12; SECOND YEAR 17: O12; SECOND YEAR 18: O12; SECOND YEAR 19: O12; SECOND YEAR 20: O12; SECOND YEAR 21: EN
48 | 31000868 | EE PROFESSOR CLAUDIO BRANDAO | BELO HORIZONTE | RMBH | A | 1610 | 1771 | Internal | 2 | 8 | FIRST YEAR 11: PRO; FIRST YEAR 12: PRO; SECOND YEAR 13: PRO; SECOND YEAR 14: PO; SECOND YEAR 15: O13; SECOND YEAR 16: O13; SECOND YEAR 17: O13; SECOND YEAR 18: O13; SECOND YEAR 19: O13; SECOND YEAR 20: O13; SECOND YEAR 21: O13; SECOND YEAR 22: O13; SECOND YEAR 23: EN
106 | 31000582 | EE PROFESSOR ALISSON PEREIRA GUIMARAES | BELO HORIZONTE | RMBH | D | 4926 | 5418.6 | Internal | 2 | 10 | FIRST YEAR 9: PRO; FIRST YEAR 10: PRO; FIRST YEAR 11: PRO; FIRST YEAR 12: PO; SECOND YEAR 13: O14; SECOND YEAR 14: O14; SECOND YEAR 15: O14; SECOND YEAR 16: O14; SECOND YEAR 17: O14; SECOND YEAR 18: O14; SECOND YEAR 19: O14; SECOND YEAR 20: O14; SECOND YEAR 21: O14; SECOND YEAR 22: O14; SECOND YEAR 23: EN
112 | 31001333 | EE LAURA DAS CHAGAS FERREIRA | BELO HORIZONTE | RMBH | A | 1680.75 | 1848.825 | Internal | 2 | 8 | FIRST YEAR 9: PRO; FIRST YEAR 10: PRO; FIRST YEAR 11: PRO; FIRST YEAR 12: PO; SECOND YEAR 13: O15; SECOND YEAR 14: O15; SECOND YEAR 15: O15; SECOND YEAR 16: O15; SECOND YEAR 17: O15; SECOND YEAR 18: O15; SECOND YEAR 19: O15; SECOND YEAR 20: O15; SECOND YEAR 21: EN
115 | 31001074 | EE CELSO MACHADO | BELO HORIZONTE | RMBH | C | 6887.6886 | 7576.4575 | Internal | 2 | 10 | FIRST YEAR 9: PRO; FIRST YEAR 10: PRO; FIRST YEAR 11: PRO; FIRST YEAR 12: PO; SECOND YEAR 13: O16; SECOND YEAR 14: O16; SECOND YEAR 15: O16; SECOND YEAR 16: O16; SECOND YEAR 17: O16; SECOND YEAR 18: O16; SECOND YEAR 19: O16; SECOND YEAR 20: O16; SECOND YEAR 21: O16; SECOND YEAR 22: O16; SECOND YEAR 23: EN
110 | 31010596 | EE GERALDO TEIXEIRA DA COSTA | SANTA LUZIA | RMBH | D | 4059.45 | 4465.395 | Internal | 2 | 10 | FIRST YEAR 11: PRO; FIRST YEAR 12: PRO; SECOND YEAR 13: PRO; SECOND YEAR 14: PO; SECOND YEAR 15: O17; SECOND YEAR 16: O17; SECOND YEAR 17: O17; SECOND YEAR 18: O17; SECOND YEAR 19: O17; SECOND YEAR 20: O17; SECOND YEAR 21: O17; SECOND YEAR 22: O17; SECOND YEAR 23: O17; SECOND YEAR 24: O17; THIRD YEAR 25: EN
10 | 31010430 | EE MARIA FLORIPES NASCIMENTO ALVES | SABARÁ | RMBH | B | 1945.27 | 2139.797 | Internal | 2 | 8 | FIRST YEAR 9: PRO; FIRST YEAR 10: PRO; FIRST YEAR 11: PRO; FIRST YEAR 12: PO; SECOND YEAR 13: O18; SECOND YEAR 14: O18; SECOND YEAR 15: O18; SECOND YEAR 16: O18; SECOND YEAR 17: O18; SECOND YEAR 18: O18; SECOND YEAR 19: O18; SECOND YEAR 20: O18; SECOND YEAR 21: EN
109 | 31010421 | EE GENERAL CARNEIRO | SABARÁ | RMBH | B | 2168.76 | 2385.636 | Internal | 2 | 8 | FIRST YEAR 11: PRO; FIRST YEAR 12: PRO; SECOND YEAR 13: PRO; SECOND YEAR 14: PO; SECOND YEAR 15: O19; SECOND YEAR 16: O19; SECOND YEAR 17: O19; SECOND YEAR 18: O19; SECOND YEAR 19: O19; SECOND YEAR 20: O19; SECOND YEAR 21: O19; SECOND YEAR 22: O19; SECOND YEAR 23: EN
120 | 31011053 | EE DEPUTADO RENATO AZEREDO | VESPASIANO | RMBH | B | 4106 | 4516.6 | Internal | 2 | 10 | FIRST YEAR 9: PRO; FIRST YEAR 10: PRO; FIRST YEAR 11: PRO; FIRST YEAR 12: PO; SECOND YEAR 13: O20; SECOND YEAR 14: O20; SECOND YEAR 15: O20; SECOND YEAR 16: O20; SECOND YEAR 17: O20; SECOND YEAR 18: O20; SECOND YEAR 19: O20; SECOND YEAR 20: O20; SECOND YEAR 21: O20; SECOND YEAR 22: O20; SECOND YEAR 23: EN
59 | 31010952 | EE PREFEITO ARISTEU EDUARDO MOREIRA | TAQUARUÇU DE MINAS | RMBH | D | 1490.57 | 1639.627 | Internal | 3 | 8 | SECOND YEAR 16: PRO; SECOND YEAR 17: PRO; SECOND YEAR 18: PRO; SECOND YEAR 19: PO; SECOND YEAR 20: O1; SECOND YEAR 21: O1; SECOND YEAR 22: O1; SECOND YEAR 23: O1; SECOND YEAR 24: O1; THIRD YEAR 25: O1; THIRD YEAR 26: O1; THIRD YEAR 27: O1; THIRD YEAR 28: EN
18 | 31007706 | EE ODILON BEHRENS | BARÃO DE COCAIS | RMBH | D | 1985 | 2183.5 | Internal | 3 | 8 | SECOND YEAR 16: PRO; SECOND YEAR 17: PRO; SECOND YEAR 18: PRO; SECOND YEAR 19: PO; SECOND YEAR 20: O2; SECOND YEAR 21: O2; SECOND YEAR 22: O2; SECOND YEAR 23: O2; SECOND YEAR 24: O2; THIRD YEAR 25: O2; THIRD YEAR 26: O2; THIRD YEAR 27: O2; THIRD YEAR 28: EN
117 | 31010511 | EE RODRIGO DE CASTRO MOREIRA PENA | SANTA BÁRBARA | RMBH | B | 2650.77 | 2915.847 | Internal | 3 | 8 | SECOND YEAR 16: PRO; SECOND YEAR 17: PRO; SECOND YEAR 18: PRO; SECOND YEAR 19: PO; SECOND YEAR 20: O3; SECOND YEAR 21: O3; SECOND YEAR 22: O3; SECOND YEAR 23: O3; SECOND YEAR 24: O3; THIRD YEAR 25: O3; THIRD YEAR 26: O3; THIRD YEAR 27: O3; THIRD YEAR 28: EN
8 | 31008338 | EE JOSÉ BRANDÃO | CAETÉ | RMBH | A | 4738.69 | 5212.559 | Internal | 3 | 10 | SECOND YEAR 19: PRO; SECOND YEAR 20: PRO; SECOND YEAR 21: PRO; SECOND YEAR 22: PO; SECOND YEAR 23: O4; SECOND YEAR 24: O4; THIRD YEAR 25: O4; THIRD YEAR 26: O4; THIRD YEAR 27: O4; THIRD YEAR 28: O4; THIRD YEAR 29: O4; THIRD YEAR 30: O4; THIRD YEAR 31: O4; THIRD YEAR 32: O4; THIRD YEAR 33: EN
114 | 31009890 | EE JOSÉ BONIFÁCIO NOGUEIRA | RIBEIRÃO DAS NEVES | RMBH | B1 | 2010.74 | 2211.814 | Internal | 3 | 8 | SECOND YEAR 17: PRO; SECOND YEAR 18: PRO; SECOND YEAR 19: PRO; SECOND YEAR 20: PO; SECOND YEAR 21: O5; SECOND YEAR 22: O5; SECOND YEAR 23: O5; SECOND YEAR 24: O5; THIRD YEAR 25: O5; THIRD YEAR 26: O5; THIRD YEAR 27: O5; THIRD YEAR 28: O5; THIRD YEAR 29: EN
113 | 31239381 | EE HENRIQUE DE SOUZA FILHO HENFIL | RIBERIÃO DAS NEVES | RMBH | B | 2287 | 2515.7 | Internal | 3 | 8 | SECOND YEAR 17: PRO; SECOND YEAR 18: PRO; SECOND YEAR 19: PRO; SECOND YEAR 20: PO; SECOND YEAR 21: O6; SECOND YEAR 22: O6; SECOND YEAR 23: O6; SECOND YEAR 24: O6; THIRD YEAR 25: O6; THIRD YEAR 26: O6; THIRD YEAR 27: O6; THIRD YEAR 28: O6; THIRD YEAR 29: EN
55 | 31009181 | EE JUSCELINO KUBITSCHECK DE OLIVEIRA | IBIRITÉ | RMBH | D | 2817.45 | 3099.195 | Internal | 3 | 10 | SECOND YEAR 17: PRO; SECOND YEAR 18: PRO; SECOND YEAR 19: PRO; SECOND YEAR 20: PO; SECOND YEAR 21: O7; SECOND YEAR 22: O7; SECOND YEAR 23: O7; SECOND YEAR 24: O7; THIRD YEAR 25: O7; THIRD YEAR 26: O7; THIRD YEAR 27: O7; THIRD YEAR 28: O7; THIRD YEAR 29: O7; THIRD YEAR 30: O7; THIRD YEAR 31: EN
11 | 31008192 | EE PAULO NETO ALKIMIM | BRUMADINHO | RMBH | A | 2842.6 | 3126.86 | Internal | 3 | 10 | SECOND YEAR 18: PRO; SECOND YEAR 19: PRO; SECOND YEAR 20: PRO; SECOND YEAR 21: PO; SECOND YEAR 22: O8; SECOND YEAR 23: O8; SECOND YEAR 24: O8; THIRD YEAR 25: O8; THIRD YEAR 26: O8; THIRD YEAR 27: O8; THIRD YEAR 28: O8; THIRD YEAR 29: O8; THIRD YEAR 30: O8; THIRD YEAR 31: O8; THIRD YEAR 32: EN
5 | 31008141 | EE PAULINA ALUOTTO FERREIRA | BRUMADINHO | RMBH | B | 2232.79 | 2456.069 | Internal | 3 | 8 | SECOND YEAR 16: PRO; SECOND YEAR 17: PRO; SECOND YEAR 18: PRO; SECOND YEAR 19: PO; SECOND YEAR 20: O9; SECOND YEAR 21: O9; SECOND YEAR 22: O9; SECOND YEAR 23: O9; SECOND YEAR 24: O9; THIRD YEAR 25: O9; THIRD YEAR 26: O9; THIRD YEAR 27: O9; THIRD YEAR 28: EN
16 | 31351075 | EE ABELARDO DUARTE PASSOS | BRUMADINHO | RMBH | B | 1130.53 | 1243.583 | Internal | 3 | 8 | SECOND YEAR 20: PRO; SECOND YEAR 21: PRO; SECOND YEAR 22: PRO; SECOND YEAR 23: PO; SECOND YEAR 24: O10; THIRD YEAR 25: O10; THIRD YEAR 26: O10; THIRD YEAR 27: O10; THIRD YEAR 28: O10; THIRD YEAR 29: O10; THIRD YEAR 30: O10; THIRD YEAR 31: O10; THIRD YEAR 32: EN
45 | 31009211 | EE PROFESSORA MARIA DE MAGALHÃES PINTO | IGARAPÉ | RMBH | B | 4253.1794 | 4678.4973 | Internal | 3 | 10 | SECOND YEAR 20: PRO; SECOND YEAR 21: PRO; SECOND YEAR 22: PRO; SECOND YEAR 23: PO; SECOND YEAR 24: O11; THIRD YEAR 25: O11; THIRD YEAR 26: O11; THIRD YEAR 27: O11; THIRD YEAR 28: O11; THIRD YEAR 29: O11; THIRD YEAR 30: O11; THIRD YEAR 31: O11; THIRD YEAR 32: O11; THIRD YEAR 33: O11; THIRD YEAR 34: EN
50 | 31034436 | EE JOAQUIM CORRÊA | JUATUBA | RMBH | A | 2060.4 | 2266.44 | Internal | 3 | 8 | SECOND YEAR 17: PRO; SECOND YEAR 18: PRO; SECOND YEAR 19: PRO; SECOND YEAR 20: PO; SECOND YEAR 21: O12; SECOND YEAR 22: O12; SECOND YEAR 23: O12; SECOND YEAR 24: O12; THIRD YEAR 25: O12; THIRD YEAR 26: O12; THIRD YEAR 27: O12; THIRD YEAR 28: O12; THIRD YEAR 29: EN
27 | 31008737 | EE FRANCISCO FIRMO DE MATOS | CONTAGEM | RMBH | D | 3304.44 | 3634.884 | Internal | 3 | 10 | SECOND YEAR 19: PRO; SECOND YEAR 20: PRO; SECOND YEAR 21: PRO; SECOND YEAR 22: PO; SECOND YEAR 23: O13; SECOND YEAR 24: O13; THIRD YEAR 25: O13; THIRD YEAR 26: O13; THIRD YEAR 27: O13; THIRD YEAR 28: O13; THIRD YEAR 29: O13; THIRD YEAR 30: O13; THIRD YEAR 31: O13; THIRD YEAR 32: O13; THIRD YEAR 33: EN
51 | 31008753 | EE HELENA GUERRA | CONTAGEM | RMBH | D1 | 2445.18 | 2689.698 | Internal | 3 | 8 | SECOND YEAR 19: PRO; SECOND YEAR 20: PRO; SECOND YEAR 21: PRO; SECOND YEAR 22: PO; SECOND YEAR 23: O14; SECOND YEAR 24: O14; THIRD YEAR 25: O14; THIRD YEAR 26: O14; THIRD YEAR 27: O14; THIRD YEAR 28: O14; THIRD YEAR 29: O14; THIRD YEAR 30: O14; THIRD YEAR 31: EN
56 | 31009407 | EE NILO MAURICIO TRINDADE FIGUEIREDO | LAGOA SANTA | RMBH | A | 3188.9 | 3507.79 | Internal | 3 | 10 | SECOND YEAR 17: PRO; SECOND YEAR 18: PRO; SECOND YEAR 19: PRO; SECOND YEAR 20: PO; SECOND YEAR 21: O15; SECOND YEAR 22: O15; SECOND YEAR 23: O15; SECOND YEAR 24: O15; THIRD YEAR 25: O15; THIRD YEAR 26: O15; THIRD YEAR 27: O15; THIRD YEAR 28: O15; THIRD YEAR 29: O15; THIRD YEAR 30: O15; THIRD YEAR 31: EN
28 | 31212598 | EE ANTÔNIO AUGUSTO RIBEIRO | BETIM | RMBH | A | 2500 | 2750 | Internal | 3 | 8 | SECOND YEAR 19: PRO; SECOND YEAR 20: PRO; SECOND YEAR 21: PRO; SECOND YEAR 22: PO; SECOND YEAR 23: O16; SECOND YEAR 24: O16; THIRD YEAR 25: O16; THIRD YEAR 26: O16; THIRD YEAR 27: O16; THIRD YEAR 28: O16; THIRD YEAR 29: O16; THIRD YEAR 30: O16; THIRD YEAR 31: EN
37 | 31212601 | EE PROFESSOR OSVALDO FRANCO | BETIM | RMBH | A | 2755.91 | 3031.501 | Internal | 3 | 10 | SECOND YEAR 21: PRO; SECOND YEAR 22: PRO; SECOND YEAR 23: PRO; SECOND YEAR 24: PO; THIRD YEAR 25: O17; THIRD YEAR 26: O17; THIRD YEAR 27: O17; THIRD YEAR 28: O17; THIRD YEAR 29: O17; THIRD YEAR 30: O17; THIRD YEAR 31: O17; THIRD YEAR 32: O17; THIRD YEAR 33: O17; THIRD YEAR 34: O17; THIRD YEAR 35: EN
25 | 31007927 | EE NOSSA SENHORA DO CARMO | BETIM | RMBH | B1 | 3028.57 | 3331.427 | Internal | 3 | 10 | SECOND YEAR 17: PRO; SECOND YEAR 18: PRO; SECOND YEAR 19: PRO; SECOND YEAR 20: PO; SECOND YEAR 21: O18; SECOND YEAR 22: O18; SECOND YEAR 23: O18; SECOND YEAR 24: O18; THIRD YEAR 25: O18; THIRD YEAR 26: O18; THIRD YEAR 27: O18; THIRD YEAR 28: O18; THIRD YEAR 29: O18; THIRD YEAR 30: O18; THIRD YEAR 31: EN
41 | 31007994 | EE CECILIA MEIRELES | BETIM | RMBH | A | 2533.2 | 2786.52 | Internal | 3 | 8 | SECOND YEAR 19: PRO; SECOND YEAR 20: PRO; SECOND YEAR 21: PRO; SECOND YEAR 22: PO; SECOND YEAR 23: O19; SECOND YEAR 24: O19; THIRD YEAR 25: O19; THIRD YEAR 26: O19; THIRD YEAR 27: O19; THIRD YEAR 28: O19; THIRD YEAR 29: O19; THIRD YEAR 30: O19; THIRD YEAR 31: EN
57 | 31002488 | EE MANOEL FERNANDES DA SILVA (BELO HORIZONTE) EE DONATO WERNECK DE FREITAS. | BELO HORIZONTE | RMBH | B | 2598 | 2857.8 | Internal | 3 | 8 | SECOND YEAR 19: PRO; SECOND YEAR 20: PRO; SECOND YEAR 21: PRO; SECOND YEAR 22: PO; SECOND YEAR 23: O20; SECOND YEAR 24: O20; THIRD YEAR 25: O20; THIRD YEAR 26: O20; THIRD YEAR 27: O20; THIRD YEAR 28: O20; THIRD YEAR 29: O20; THIRD YEAR 30: O20; THIRD YEAR 31: EN
53 | 31002500 | EE MARIA LUIZA MIRANDA BASTOS | BELO HORIZONTE | RMBH | D | 2843.25 | 3127.575 | Internal | 3 | 10 | SECOND YEAR 24: PRO; THIRD YEAR 25: PRO; THIRD YEAR 26: PRO; THIRD YEAR 27: PO; THIRD YEAR 28: O2; THIRD YEAR 29: O2; THIRD YEAR 30: O2; THIRD YEAR 31: O2; THIRD YEAR 32: O2; THIRD YEAR 33: O2; THIRD YEAR 34: O2; THIRD YEAR 35: O2; THIRD YEAR 36: O2; FOURTH YEAR 37: O2; FOURTH YEAR 38: EN

## Global Lot
| Temporary Structure Scenarios |  |  | Legend
| Up to 1000 m² | 4 months of construction |  | PRO | Work Delivery and Acceptance
| From 1000 to 3000 m² | 6 months of construction |  | PO | Pre-Construction Period – Approvals
| Above 3000 m² | 8 months of construction |  | EP | Temporary Structure Assembly / Disassembly
| No-Migration Scenarios |  |  | O | Construction Period **Numbers indicate work teams
| Up to 1000 m² | 6 months of construction |  | EN | Entrega e Aceite de Obra
| From 1000 to 3000 m² | 8 months of construction
| Above 3000 m² | 10 months of construction
[10 empty] | FIRST YEAR | [11 empty] | SECOND YEAR | [11 empty] | THIRD YEAR | [11 empty] | FOURTH YEAR | [11 empty] | FIFTH YEAR
ID | INEP Code | School Unit | Municipality | Sub-lot | Typology | Built Area | Built Area (with 10% increase) | Relocation Scenario | Construction Period (month) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
31 | 31007862 | EE JOÃO PAULO I | BETIM | RMBH | B1 | 2548.82 | 2803.702 | Shared Temporary Structure | 6 | FIRST YEAR 1: PRO; FIRST YEAR 2: PRO; FIRST YEAR 3: PRO; FIRST YEAR 4: PO; FIRST YEAR 5: EP; FIRST YEAR 6: O1; FIRST YEAR 7: O1; FIRST YEAR 8: O1; FIRST YEAR 9: O1; FIRST YEAR 10: O1; FIRST YEAR 11: O1; FIRST YEAR 12: EN; SECOND YEAR 13: EP
62 | 31010812 | EE RENY DE SOUZA LIMA | SANTA LUZIA | RMBH | A1 | 1784.89 | 1963.379 | Shared Temporary Structure | 6 | FIRST YEAR 1: PRO; FIRST YEAR 2: PRO; FIRST YEAR 3: PRO; FIRST YEAR 4: PO; FIRST YEAR 5: EP; FIRST YEAR 6: O2; FIRST YEAR 7: O2; FIRST YEAR 8: O2; FIRST YEAR 9: O2; FIRST YEAR 10: O2; FIRST YEAR 11: O2; FIRST YEAR 12: EN; SECOND YEAR 13: EP
14 | 31010456 | EE JOSÉ LUIZ GONZAGA FERREIRA | SABARÁ | RMBH | A1 | 1507.85 | 1658.635 | Shared Temporary Structure | 6 | FIRST YEAR 1: PRO; FIRST YEAR 2: PRO; FIRST YEAR 3: PRO; FIRST YEAR 4: PO; FIRST YEAR 5: EP; FIRST YEAR 6: O3; FIRST YEAR 7: O3; FIRST YEAR 8: O3; FIRST YEAR 9: O3; FIRST YEAR 10: O3; FIRST YEAR 11: O3; FIRST YEAR 12: EN; SECOND YEAR 13: EP
108 | 31010251 | EE SANTO ANTÔNIO | RIO ACIMA | RMBH | A2 | 2613.88 | 2875.268 | Partial Temporary Structure | 6 | FIRST YEAR 1: PRO; FIRST YEAR 2: PRO; FIRST YEAR 3: PRO; FIRST YEAR 4: PO; FIRST YEAR 5: EP; FIRST YEAR 6: O4; FIRST YEAR 7: O4; FIRST YEAR 8: O4; FIRST YEAR 9: O4; FIRST YEAR 10: O4; FIRST YEAR 11: O4; FIRST YEAR 12: EN; SECOND YEAR 13: EP
35 | 31007838 | EE NASCIMENTO NUNES LEAL | BETIM | RMBH | B2 | 1748.42 | 1923.262 | Partial Temporary Structure | 6 | FIRST YEAR 1: PRO; FIRST YEAR 2: PRO; FIRST YEAR 3: PRO; FIRST YEAR 4: PO; FIRST YEAR 5: EP; FIRST YEAR 6: O5; FIRST YEAR 7: O5; FIRST YEAR 8: O5; FIRST YEAR 9: O5; FIRST YEAR 10: O5; FIRST YEAR 11: O5; FIRST YEAR 12: EN; SECOND YEAR 13: EP
36 | 31007951 | EE SENADOR TEOTONIO VILELA | BETIM | RMBH | B | 1897.59 | 2087.349 | Internal | 8 | FIRST YEAR 1: PRO; FIRST YEAR 2: PRO; FIRST YEAR 3: PRO; FIRST YEAR 4: PO; FIRST YEAR 5: O6; FIRST YEAR 6: O6; FIRST YEAR 7: O6; FIRST YEAR 8: O6; FIRST YEAR 9: O6; FIRST YEAR 10: O6; FIRST YEAR 11: O6; FIRST YEAR 12: O6; SECOND YEAR 13: EN
26 | 31008028 | EE DO BAIRRO SÃO CAETANO | BETIM | RMBH | D | 2845.55 | 3130.105 | Internal | 10 | FIRST YEAR 1: PRO; FIRST YEAR 2: PRO; FIRST YEAR 3: PRO; FIRST YEAR 4: PO; FIRST YEAR 5: O7; FIRST YEAR 6: O7; FIRST YEAR 7: O7; FIRST YEAR 8: O7; FIRST YEAR 9: O7; FIRST YEAR 10: O7; FIRST YEAR 11: O7; FIRST YEAR 12: O7; SECOND YEAR 13: O7; SECOND YEAR 14: O7; SECOND YEAR 15: EN
13 | 31001317 | EE CORAÇÃO EUCARÍSTICO | BELO HORIZONTE | RMBH | B | 1509.16 | 1660.076 | Internal | 8 | FIRST YEAR 1: PRO; FIRST YEAR 2: PRO; FIRST YEAR 3: PRO; FIRST YEAR 4: PO; FIRST YEAR 5: O8; FIRST YEAR 6: O8; FIRST YEAR 7: O8; FIRST YEAR 8: O8; FIRST YEAR 9: O8; FIRST YEAR 10: O8; FIRST YEAR 11: O8; FIRST YEAR 12: O8; SECOND YEAR 13: EN
32 | 31000795 | EE MINISTRO ALFREDO VILHENA VALLADÃO | BELO HORIZONTE | RMBH | B | 2618.42 | 2880.262 | Internal | 8 | FIRST YEAR 1: PRO; FIRST YEAR 2: PRO; FIRST YEAR 3: PRO; FIRST YEAR 4: PO; FIRST YEAR 5: O9; FIRST YEAR 6: O9; FIRST YEAR 7: O9; FIRST YEAR 8: O9; FIRST YEAR 9: O9; FIRST YEAR 10: O9; FIRST YEAR 11: O9; FIRST YEAR 12: O9; SECOND YEAR 13: EN
43 | 31001694 | EE PADRE MATIAS | BELO HORIZONTE | RMBH | D1 | 1914.72 | 2106.192 | Internal | 8 | FIRST YEAR 1: PRO; FIRST YEAR 2: PRO; FIRST YEAR 3: PRO; FIRST YEAR 4: PO; FIRST YEAR 5: O10; FIRST YEAR 6: O10; FIRST YEAR 7: O10; FIRST YEAR 8: O10; FIRST YEAR 9: O10; FIRST YEAR 10: O10; FIRST YEAR 11: O10; FIRST YEAR 12: O10; SECOND YEAR 13: EN
63 | 31062472 | EE OLEGARIO MACIEL | JANUÁRIA | North | D1 | 3271.26 | 3598.386 | Internal | 10 | FIRST YEAR 1: PRO; FIRST YEAR 2: PRO; FIRST YEAR 3: PRO; FIRST YEAR 4: PO; FIRST YEAR 5: O11; FIRST YEAR 6: O11; FIRST YEAR 7: O11; FIRST YEAR 8: O11; FIRST YEAR 9: O11; FIRST YEAR 10: O11; FIRST YEAR 11: O11; FIRST YEAR 12: O11; SECOND YEAR 13: O11; SECOND YEAR 14: O11; SECOND YEAR 15: EN
69 | 31062642 | EE MONSENHOR FLORISVAL MONTALVAO | JANUÁRIA | North | A | 2937 | 3230.7 | Internal | 10 | FIRST YEAR 1: PRO; FIRST YEAR 2: PRO; FIRST YEAR 3: PRO; FIRST YEAR 4: PO; FIRST YEAR 5: O12; FIRST YEAR 6: O12; FIRST YEAR 7: O12; FIRST YEAR 8: O12; FIRST YEAR 9: O12; FIRST YEAR 10: O12; FIRST YEAR 11: O12; FIRST YEAR 12: O12; SECOND YEAR 13: O12; SECOND YEAR 14: O12; SECOND YEAR 15: EN
95 | 31081264 | EE PROFESSOR PLINIO RIBEIRO | MONTES CLAROS | North | B | 8006.1 | 8806.71 | Internal | 10 | FIRST YEAR 1: PRO; FIRST YEAR 2: PRO; FIRST YEAR 3: PRO; FIRST YEAR 4: PO; FIRST YEAR 5: O13; FIRST YEAR 6: O13; FIRST YEAR 7: O13; FIRST YEAR 8: O13; FIRST YEAR 9: O13; FIRST YEAR 10: O13; FIRST YEAR 11: O13; FIRST YEAR 12: O13; SECOND YEAR 13: O13; SECOND YEAR 14: O13; SECOND YEAR 15: EN
98 | 31081795 | EE PROFESSOR ALCIDES DE CARVALHO | MONTES CLAROS | North | A | 5157 | 5672.7 | Internal | 10 | FIRST YEAR 1: PRO; FIRST YEAR 2: PRO; FIRST YEAR 3: PRO; FIRST YEAR 4: PO; FIRST YEAR 5: O14; FIRST YEAR 6: O14; FIRST YEAR 7: O14; FIRST YEAR 8: O14; FIRST YEAR 9: O14; FIRST YEAR 10: O14; FIRST YEAR 11: O14; FIRST YEAR 12: O14; SECOND YEAR 13: O14; SECOND YEAR 14: O14; SECOND YEAR 15: EN
88 | 31081400 | EE ARMÊNIO VELOSO | MONTES CLAROS | North | B | 2116.74 | 2328.414 | Internal | 8 | FIRST YEAR 1: PRO; FIRST YEAR 2: PRO; FIRST YEAR 3: PRO; FIRST YEAR 4: PO; FIRST YEAR 5: O15; FIRST YEAR 6: O15; FIRST YEAR 7: O15; FIRST YEAR 8: O15; FIRST YEAR 9: O15; FIRST YEAR 10: O15; FIRST YEAR 11: O15; FIRST YEAR 12: O15; SECOND YEAR 13: EN
87 | 31079863 | EE BENICIO PRATES | CORAÇÃO DE JESUS | North | A | 2251.0605 | 2476.1665 | Internal | 8 | FIRST YEAR 1: PRO; FIRST YEAR 2: PRO; FIRST YEAR 3: PRO; FIRST YEAR 4: PO; FIRST YEAR 5: O16; FIRST YEAR 6: O16; FIRST YEAR 7: O16; FIRST YEAR 8: O16; FIRST YEAR 9: O16; FIRST YEAR 10: O16; FIRST YEAR 11: O16; FIRST YEAR 12: O16; SECOND YEAR 13: EN
90 | 31079944 | EE CORONEL LUIS PIRES DE MINAS | CORAÇÃO DE JESUS | North | A | 2529 | 2781.9 | Internal | 8 | FIRST YEAR 1: PRO; FIRST YEAR 2: PRO; FIRST YEAR 3: PRO; FIRST YEAR 4: PO; FIRST YEAR 5: O17; FIRST YEAR 6: O17; FIRST YEAR 7: O17; FIRST YEAR 8: O17; FIRST YEAR 9: O17; FIRST YEAR 10: O17; FIRST YEAR 11: O17; FIRST YEAR 12: O17; SECOND YEAR 13: EN
100 | 31239241 | EE SAO JOSE | CORAÇÃO DE JESUS | North | A | 1508.45 | 1659.295 | Internal | 8 | FIRST YEAR 1: PRO; FIRST YEAR 2: PRO; FIRST YEAR 3: PRO; FIRST YEAR 4: PO; FIRST YEAR 5: O18; FIRST YEAR 6: O18; FIRST YEAR 7: O18; FIRST YEAR 8: O18; FIRST YEAR 9: O18; FIRST YEAR 10: O18; FIRST YEAR 11: O18; FIRST YEAR 12: O18; SECOND YEAR 13: EN
79 | 31079383 | EE ZINHA MEIRA | BOCAIÚVA | North | A | 3487.04 | 3835.744 | Internal | 10 | FIRST YEAR 1: PRO; FIRST YEAR 2: PRO; FIRST YEAR 3: PRO; FIRST YEAR 4: PO; FIRST YEAR 5: O19; FIRST YEAR 6: O19; FIRST YEAR 7: O19; FIRST YEAR 8: O19; FIRST YEAR 9: O19; FIRST YEAR 10: O19; FIRST YEAR 11: O19; FIRST YEAR 12: O19; SECOND YEAR 13: O19; SECOND YEAR 14: O19; SECOND YEAR 15: EN
81 | 31079448 | EE PROFESSOR GASTAO VALLE | BOCAIÚVA | North | D | 3926 | 4318.6 | Internal | 10 | FIRST YEAR 1: PRO; FIRST YEAR 2: PRO; FIRST YEAR 3: PRO; FIRST YEAR 4: PO; FIRST YEAR 5: O20; FIRST YEAR 6: O20; FIRST YEAR 7: O20; FIRST YEAR 8: O20; FIRST YEAR 9: O20; FIRST YEAR 10: O20; FIRST YEAR 11: O20; FIRST YEAR 12: O20; SECOND YEAR 13: O20; SECOND YEAR 14: O20; SECOND YEAR 15: EN
46 | 31007854 | EE AMELIA SANTANA BARBOSA | BETIM | RMBH | B | 4583.4 | 5041.74 | Internal | 10 | FIRST YEAR 7: PRO; FIRST YEAR 8: PRO; FIRST YEAR 9: PRO; FIRST YEAR 10: PO; FIRST YEAR 11: O4; FIRST YEAR 12: O4; SECOND YEAR 13: O4; SECOND YEAR 14: O4; SECOND YEAR 15: O4; SECOND YEAR 16: O4; SECOND YEAR 17: O4; SECOND YEAR 18: O4; SECOND YEAR 19: O4; SECOND YEAR 20: O4; SECOND YEAR 21: EN
49 | 31007901 | EE JUSCELINO KUBITSCHEK DE OLIVEIRA | BETIM | RMBH | B1 | 2168.02 | 2384.822 | Internal | 8 | FIRST YEAR 8: PRO; FIRST YEAR 9: PRO; FIRST YEAR 10: PRO; FIRST YEAR 11: PO; FIRST YEAR 12: O5; SECOND YEAR 13: O5; SECOND YEAR 14: O5; SECOND YEAR 15: O5; SECOND YEAR 16: O5; SECOND YEAR 17: O5; SECOND YEAR 18: O5; SECOND YEAR 19: O5; SECOND YEAR 20: EN
111 | 31002071 | EE ISABEL DA SILVA POLCK | BELO HORIZONTE | RMBH | A | 1637.39 | 1801.129 | Internal | 8 | FIRST YEAR 8: PRO; FIRST YEAR 9: PRO; FIRST YEAR 10: PRO; FIRST YEAR 11: PO; FIRST YEAR 12: O6; SECOND YEAR 13: O6; SECOND YEAR 14: O6; SECOND YEAR 15: O6; SECOND YEAR 16: O6; SECOND YEAR 17: O6; SECOND YEAR 18: O6; SECOND YEAR 19: O6; SECOND YEAR 20: EN
47 | 31001791 | EE DESEMBARGADOR RODRIGUES CAMPOS | BELO HORIZONTE | RMBH | A | 1932.2 | 2125.42 | Internal | 8 | FIRST YEAR 10: PRO; FIRST YEAR 11: PRO; FIRST YEAR 12: PRO; SECOND YEAR 13: PO; SECOND YEAR 14: O7; SECOND YEAR 15: O7; SECOND YEAR 16: O7; SECOND YEAR 17: O7; SECOND YEAR 18: O7; SECOND YEAR 19: O7; SECOND YEAR 20: O7; SECOND YEAR 21: O7; SECOND YEAR 22: EN
48 | 31000868 | EE PROFESSOR CLAUDIO BRANDAO | BELO HORIZONTE | RMBH | A | 1610 | 1771 | Internal | 8 | FIRST YEAR 8: PRO; FIRST YEAR 9: PRO; FIRST YEAR 10: PRO; FIRST YEAR 11: PO; FIRST YEAR 12: O8; SECOND YEAR 13: O8; SECOND YEAR 14: O8; SECOND YEAR 15: O8; SECOND YEAR 16: O8; SECOND YEAR 17: O8; SECOND YEAR 18: O8; SECOND YEAR 19: O8; SECOND YEAR 20: EN
17 | 31001261 | EE PROFESSOR LEOPOLDO DE MIRANDA | BELO HORIZONTE | RMBH | B1 | 1068.33 | 1175.163 | Shared Temporary Structure | 6 | FIRST YEAR 9: PRO; FIRST YEAR 10: PRO; FIRST YEAR 11: PRO; FIRST YEAR 12: PO; SECOND YEAR 13: EP; SECOND YEAR 14: O1; SECOND YEAR 15: O1; SECOND YEAR 16: O1; SECOND YEAR 17: O1; SECOND YEAR 18: O1; SECOND YEAR 19: O1; SECOND YEAR 20: EN; SECOND YEAR 21: EP
22 | 31007811 | EE CONSELHEIRO AFONSO PENA | BETIM | RMBH | B1 | 1992 | 2191.2 | Shared Temporary Structure | 6 | FIRST YEAR 9: PRO; FIRST YEAR 10: PRO; FIRST YEAR 11: PRO; FIRST YEAR 12: PO; SECOND YEAR 13: EP; SECOND YEAR 14: O2; SECOND YEAR 15: O2; SECOND YEAR 16: O2; SECOND YEAR 17: O2; SECOND YEAR 18: O2; SECOND YEAR 19: O2; SECOND YEAR 20: EN; SECOND YEAR 21: EP
107 | 31010618 | EE JOSÉ MARIA BICALHO | SANTA LUZIA | RMBH | A | 2016.28 | 2217.908 | Shared Temporary Structure | 6 | FIRST YEAR 9: PRO; FIRST YEAR 10: PRO; FIRST YEAR 11: PRO; FIRST YEAR 12: PO; SECOND YEAR 13: EP; SECOND YEAR 14: O3; SECOND YEAR 15: O3; SECOND YEAR 16: O3; SECOND YEAR 17: O3; SECOND YEAR 18: O3; SECOND YEAR 19: O3; SECOND YEAR 20: EN; SECOND YEAR 21: EP
105 | 31010731 | EE LEONINA MOURTHÉ | SANTA LUZIA | RMBH | B | 2346.72 | 2581.392 | Internal | 8 | FIRST YEAR 8: PRO; FIRST YEAR 9: PRO; FIRST YEAR 10: PRO; FIRST YEAR 11: PO; FIRST YEAR 12: O9; SECOND YEAR 13: O9; SECOND YEAR 14: O9; SECOND YEAR 15: O9; SECOND YEAR 16: O9; SECOND YEAR 17: O9; SECOND YEAR 18: O9; SECOND YEAR 19: O9; SECOND YEAR 20: EN
110 | 31010596 | EE GERALDO TEIXEIRA DA COSTA | SANTA LUZIA | RMBH | D | 4059.45 | 4465.395 | Internal | 10 | FIRST YEAR 8: PRO; FIRST YEAR 9: PRO; FIRST YEAR 10: PRO; FIRST YEAR 11: PO; FIRST YEAR 12: O10; SECOND YEAR 13: O10; SECOND YEAR 14: O10; SECOND YEAR 15: O10; SECOND YEAR 16: O10; SECOND YEAR 17: O10; SECOND YEAR 18: O10; SECOND YEAR 19: O10; SECOND YEAR 20: O10; SECOND YEAR 21: O10; SECOND YEAR 22: EN
76 | 31081418 | EE AUGUSTA VALLE | MONTES CLAROS | North | A | 3188.4024 | 3507.2427 | Internal | 10 | FIRST YEAR 10: PRO; FIRST YEAR 11: PRO; FIRST YEAR 12: PRO; SECOND YEAR 13: PO; SECOND YEAR 14: O11; SECOND YEAR 15: O11; SECOND YEAR 16: O11; SECOND YEAR 17: O11; SECOND YEAR 18: O11; SECOND YEAR 19: O11; SECOND YEAR 20: O11; SECOND YEAR 21: O11; SECOND YEAR 22: O11; SECOND YEAR 23: O11; SECOND YEAR 24: EN
77 | 31081396 | EE DOUTOR CARLOS ALBUQUERQUE | MONTES CLAROS | North | A | 3165.9219 | 3482.514 | Internal | 10 | FIRST YEAR 8: PRO; FIRST YEAR 9: PRO; FIRST YEAR 10: PRO; FIRST YEAR 11: PO; FIRST YEAR 12: O17; SECOND YEAR 13: O17; SECOND YEAR 14: O17; SECOND YEAR 15: O17; SECOND YEAR 16: O17; SECOND YEAR 17: O17; SECOND YEAR 18: O17; SECOND YEAR 19: O17; SECOND YEAR 20: O17; SECOND YEAR 21: O17; SECOND YEAR 22: EN
83 | 31081485 | EE DELFINO MAGALHAES | MONTES CLAROS | North | A | 2752.35 | 3027.585 | Internal | 10 | FIRST YEAR 10: PRO; FIRST YEAR 11: PRO; FIRST YEAR 12: PRO; SECOND YEAR 13: PO; SECOND YEAR 14: O12; SECOND YEAR 15: O12; SECOND YEAR 16: O12; SECOND YEAR 17: O12; SECOND YEAR 18: O12; SECOND YEAR 19: O12; SECOND YEAR 20: O12; SECOND YEAR 21: O12; SECOND YEAR 22: O12; SECOND YEAR 23: O12; SECOND YEAR 24: EN
91 | 31205664 | EE LEVI DURAES PERES | MONTES CLAROS | North | D | 4241 | 4665.1 | Internal | 10 | FIRST YEAR 10: PRO; FIRST YEAR 11: PRO; FIRST YEAR 12: PRO; SECOND YEAR 13: PO; SECOND YEAR 14: O13; SECOND YEAR 15: O13; SECOND YEAR 16: O13; SECOND YEAR 17: O13; SECOND YEAR 18: O13; SECOND YEAR 19: O13; SECOND YEAR 20: O13; SECOND YEAR 21: O13; SECOND YEAR 22: O13; SECOND YEAR 23: O13; SECOND YEAR 24: EN
97 | 31081540 | EE PROFESSORA DILMA QUADROS | MONTES CLAROS | North | B | 2184.3 | 2402.73 | Internal | 8 | FIRST YEAR 10: PRO; FIRST YEAR 11: PRO; FIRST YEAR 12: PRO; SECOND YEAR 13: PO; SECOND YEAR 14: O14; SECOND YEAR 15: O14; SECOND YEAR 16: O14; SECOND YEAR 17: O14; SECOND YEAR 18: O14; SECOND YEAR 19: O14; SECOND YEAR 20: O14; SECOND YEAR 21: O14; SECOND YEAR 22: EN
101 | 31081434 | EE MARIA DA CONCEICAO RODRIGUES AVELAR | MONTES CLAROS | North | D | 2919 | 3210.9 | Internal | 10 | FIRST YEAR 8: PRO; FIRST YEAR 9: PRO; FIRST YEAR 10: PRO; FIRST YEAR 11: PO; FIRST YEAR 12: O15; SECOND YEAR 13: O15; SECOND YEAR 14: O15; SECOND YEAR 15: O15; SECOND YEAR 16: O15; SECOND YEAR 17: O15; SECOND YEAR 18: O15; SECOND YEAR 19: O15; SECOND YEAR 20: O15; SECOND YEAR 21: O15; SECOND YEAR 22: EN
84 | 31081809 | EE PROFESSORA DULCE SARMENTO | MONTES CLAROS | North | D | 1960.32 | 2156.352 | Internal | 8 | FIRST YEAR 8: PRO; FIRST YEAR 9: PRO; FIRST YEAR 10: PRO; FIRST YEAR 11: PO; FIRST YEAR 12: O16; SECOND YEAR 13: O16; SECOND YEAR 14: O16; SECOND YEAR 15: O16; SECOND YEAR 16: O16; SECOND YEAR 17: O16; SECOND YEAR 18: O16; SECOND YEAR 19: O16; SECOND YEAR 20: EN
78 | 31081591 | EE ELOY PEREIRA | MONTES CLAROS | North | B | 2127 | 2339.7 | Internal | 8 | FIRST YEAR 8: PRO; FIRST YEAR 9: PRO; FIRST YEAR 10: PRO; FIRST YEAR 11: PO; FIRST YEAR 12: O18; SECOND YEAR 13: O18; SECOND YEAR 14: O18; SECOND YEAR 15: O18; SECOND YEAR 16: O18; SECOND YEAR 17: O18; SECOND YEAR 18: O18; SECOND YEAR 19: O18; SECOND YEAR 20: EN
85 | 31082678 | EE GUIMARAES ROSA | LONTRA | North | B | 2574.59 | 2832.049 | Internal | 8 | FIRST YEAR 10: PRO; FIRST YEAR 11: PRO; FIRST YEAR 12: PRO; SECOND YEAR 13: PO; SECOND YEAR 14: O19; SECOND YEAR 15: O19; SECOND YEAR 16: O19; SECOND YEAR 17: O19; SECOND YEAR 18: O19; SECOND YEAR 19: O19; SECOND YEAR 20: O19; SECOND YEAR 21: O19; SECOND YEAR 22: EN
93 | 31080900 | EE PROFESSORA MARIA MACHADO | MIRABELA | North | B | 2939 | 3232.9 | Internal | 10 | FIRST YEAR 10: PRO; FIRST YEAR 11: PRO; FIRST YEAR 12: PRO; SECOND YEAR 13: PO; SECOND YEAR 14: O20; SECOND YEAR 15: O20; SECOND YEAR 16: O20; SECOND YEAR 17: O20; SECOND YEAR 18: O20; SECOND YEAR 19: O20; SECOND YEAR 20: O20; SECOND YEAR 21: O20; SECOND YEAR 22: O20; SECOND YEAR 23: O20; SECOND YEAR 24: EN
59 | 31010952 | EE PREFEITO ARISTEU EDUARDO MOREIRA | TAQUARUÇU DE MINAS | RMBH | D | 1490.57 | 1639.627 | Internal | 8 | SECOND YEAR 19: PRO; SECOND YEAR 20: PRO; SECOND YEAR 21: PRO; SECOND YEAR 22: PO; SECOND YEAR 23: O11; SECOND YEAR 24: O11; THIRD YEAR 25: O11; THIRD YEAR 26: O11; THIRD YEAR 27: O11; THIRD YEAR 28: O11; THIRD YEAR 29: O11; THIRD YEAR 30: O11; THIRD YEAR 31: EN
120 | 31011053 | EE DEPUTADO RENATO AZEREDO | VESPASIANO | RMBH | B | 4106 | 4516.6 | Internal | 10 | SECOND YEAR 19: PRO; SECOND YEAR 20: PRO; SECOND YEAR 21: PRO; SECOND YEAR 22: PO; SECOND YEAR 23: O12; SECOND YEAR 24: O12; THIRD YEAR 25: O12; THIRD YEAR 26: O12; THIRD YEAR 27: O12; THIRD YEAR 28: O12; THIRD YEAR 29: O12; THIRD YEAR 30: O12; THIRD YEAR 31: O12; THIRD YEAR 32: O12; THIRD YEAR 33: EN
58 | 31009679 | EE IMACULADA CONCEIÇÃO | PEDRO LEOPOLDO | RMBH | D1 | 3180.22 | 3498.242 | Dedicated Temporary Structure | 8 | SECOND YEAR 17: PRO; SECOND YEAR 18: PRO; SECOND YEAR 19: PRO; SECOND YEAR 20: PO; SECOND YEAR 21: EP; SECOND YEAR 22: O1; SECOND YEAR 23: O1; SECOND YEAR 24: O1; THIRD YEAR 25: O1; THIRD YEAR 26: O1; THIRD YEAR 27: O1; THIRD YEAR 28: O1; THIRD YEAR 29: O1; THIRD YEAR 30: EN; THIRD YEAR 31: EP
3 | 31009539 | EE AUGUSTO DE LIMA (NOVA LIMA) | NOVA LIMA | RMBH | B1 | 3839.32 | 4223.252 | Dedicated Temporary Structure | 8 | SECOND YEAR 17: PRO; SECOND YEAR 18: PRO; SECOND YEAR 19: PRO; SECOND YEAR 20: PO; SECOND YEAR 21: EP; SECOND YEAR 22: O2; SECOND YEAR 23: O2; SECOND YEAR 24: O2; THIRD YEAR 25: O2; THIRD YEAR 26: O2; THIRD YEAR 27: O2; THIRD YEAR 28: O2; THIRD YEAR 29: O2; THIRD YEAR 30: EN; THIRD YEAR 31: EP
45 | 31009211 | EE PROFESSORA MARIA DE MAGALHÃES PINTO | IGARAPÉ | RMBH | B | 4253.1794 | 4678.4973 | Internal | 10 | SECOND YEAR 15: PRO; SECOND YEAR 16: PRO; SECOND YEAR 17: PRO; SECOND YEAR 18: PO; SECOND YEAR 19: O3; SECOND YEAR 20: O3; SECOND YEAR 21: O3; SECOND YEAR 22: O3; SECOND YEAR 23: O3; SECOND YEAR 24: O3; THIRD YEAR 25: O3; THIRD YEAR 26: O3; THIRD YEAR 27: O3; THIRD YEAR 28: O3; THIRD YEAR 29: EN
55 | 31009181 | EE JUSCELINO KUBITSCHECK DE OLIVEIRA | IBIRITÉ | RMBH | D | 2817.45 | 3099.195 | Internal | 10 | SECOND YEAR 16: PRO; SECOND YEAR 17: PRO; SECOND YEAR 18: PRO; SECOND YEAR 19: PO; SECOND YEAR 20: O4; SECOND YEAR 21: O4; SECOND YEAR 22: O4; SECOND YEAR 23: O4; SECOND YEAR 24: O4; THIRD YEAR 25: O4; THIRD YEAR 26: O4; THIRD YEAR 27: O4; THIRD YEAR 28: O4; THIRD YEAR 29: O4; THIRD YEAR 30: EN
117 | 31010511 | EE RODRIGO DE CASTRO MOREIRA PENA | SANTA BÁRBARA | RMBH | B | 2650.77 | 2915.847 | Internal | 8 | SECOND YEAR 15: PRO; SECOND YEAR 16: PRO; SECOND YEAR 17: PRO; SECOND YEAR 18: PO; SECOND YEAR 19: O5; SECOND YEAR 20: O5; SECOND YEAR 21: O5; SECOND YEAR 22: O5; SECOND YEAR 23: O5; SECOND YEAR 24: O5; THIRD YEAR 25: O5; THIRD YEAR 26: O5; THIRD YEAR 27: EN
8 | 31008338 | EE JOSÉ BRANDÃO | CAETÉ | RMBH | A | 4738.69 | 5212.559 | Internal | 10 | SECOND YEAR 15: PRO; SECOND YEAR 16: PRO; SECOND YEAR 17: PRO; SECOND YEAR 18: PO; SECOND YEAR 19: O6; SECOND YEAR 20: O6; SECOND YEAR 21: O6; SECOND YEAR 22: O6; SECOND YEAR 23: O6; SECOND YEAR 24: O6; THIRD YEAR 25: O6; THIRD YEAR 26: O6; THIRD YEAR 27: O6; THIRD YEAR 28: O6; THIRD YEAR 29: EN
18 | 31007706 | EE ODILON BEHRENS | BARÃO DE COCAIS | RMBH | D | 1985 | 2183.5 | Internal | 8 | SECOND YEAR 17: PRO; SECOND YEAR 18: PRO; SECOND YEAR 19: PRO; SECOND YEAR 20: PO; SECOND YEAR 21: O7; SECOND YEAR 22: O7; SECOND YEAR 23: O7; SECOND YEAR 24: O7; THIRD YEAR 25: O7; THIRD YEAR 26: O7; THIRD YEAR 27: O7; THIRD YEAR 28: O7; THIRD YEAR 29: EN
113 | 31239381 | EE HENRIQUE DE SOUZA FILHO HENFIL | RIBERIÃO DAS NEVES | RMBH | B | 2287 | 2515.7 | Internal | 8 | SECOND YEAR 15: PRO; SECOND YEAR 16: PRO; SECOND YEAR 17: PRO; SECOND YEAR 18: PO; SECOND YEAR 19: O8; SECOND YEAR 20: O8; SECOND YEAR 21: O8; SECOND YEAR 22: O8; SECOND YEAR 23: O8; SECOND YEAR 24: O8; THIRD YEAR 25: O8; THIRD YEAR 26: O8; THIRD YEAR 27: EN
114 | 31009890 | EE JOSÉ BONIFÁCIO NOGUEIRA | RIBEIRÃO DAS NEVES | RMBH | B1 | 2010.74 | 2211.814 | Internal | 8 | SECOND YEAR 15: PRO; SECOND YEAR 16: PRO; SECOND YEAR 17: PRO; SECOND YEAR 18: PO; SECOND YEAR 19: O9; SECOND YEAR 20: O9; SECOND YEAR 21: O9; SECOND YEAR 22: O9; SECOND YEAR 23: O9; SECOND YEAR 24: O9; THIRD YEAR 25: O9; THIRD YEAR 26: O9; THIRD YEAR 27: EN
103 | 31000841 | EE DOUTOR AURINO MORAIS | BELO HORIZONTE | RMBH | B | 4106.45 | 4517.095 | Internal | 10 | SECOND YEAR 17: PRO; SECOND YEAR 18: PRO; SECOND YEAR 19: PRO; SECOND YEAR 20: PO; SECOND YEAR 21: O10; SECOND YEAR 22: O10; SECOND YEAR 23: O10; SECOND YEAR 24: O10; THIRD YEAR 25: O10; THIRD YEAR 26: O10; THIRD YEAR 27: O10; THIRD YEAR 28: O10; THIRD YEAR 29: O10; THIRD YEAR 30: O10; THIRD YEAR 31: EN
67 | 31063096 | EE DONA ALICE MENDONCA | SÃO FRANCISCO | North | B | 1901.3 | 2091.43 | Internal | 8 | SECOND YEAR 19: PRO; SECOND YEAR 20: PRO; SECOND YEAR 21: PRO; SECOND YEAR 22: PO; SECOND YEAR 23: O13; SECOND YEAR 24: O13; THIRD YEAR 25: O13; THIRD YEAR 26: O13; THIRD YEAR 27: O13; THIRD YEAR 28: O13; THIRD YEAR 29: O13; THIRD YEAR 30: O13; THIRD YEAR 31: EN
64 | 31240222 | EE BRASILIANO BRAZ | SÃO FRANCISCO | North | A | 4980.72 | 5478.792 | Internal | 10 | SECOND YEAR 17: PRO; SECOND YEAR 18: PRO; SECOND YEAR 19: PRO; SECOND YEAR 20: PO; SECOND YEAR 21: O14; SECOND YEAR 22: O14; SECOND YEAR 23: O14; SECOND YEAR 24: O14; THIRD YEAR 25: O14; THIRD YEAR 26: O14; THIRD YEAR 27: O14; THIRD YEAR 28: O14; THIRD YEAR 29: O14; THIRD YEAR 30: O14; THIRD YEAR 31: EN
65 | 31062308 | EE PROFESSOR JOSEFINO BARBOSA | ITACARAMBI | North | B | 4014 | 4415.4 | Internal | 10 | SECOND YEAR 17: PRO; SECOND YEAR 18: PRO; SECOND YEAR 19: PRO; SECOND YEAR 20: PO; SECOND YEAR 21: O15; SECOND YEAR 22: O15; SECOND YEAR 23: O15; SECOND YEAR 24: O15; THIRD YEAR 25: O15; THIRD YEAR 26: O15; THIRD YEAR 27: O15; THIRD YEAR 28: O15; THIRD YEAR 29: O15; THIRD YEAR 30: O15; THIRD YEAR 31: EN
82 | 31080918 | EE FRANCISCO ANDRADE | PATIS | North | B | 2038 | 2241.8 | Internal | 8 | SECOND YEAR 15: PRO; SECOND YEAR 16: PRO; SECOND YEAR 17: PRO; SECOND YEAR 18: PO; SECOND YEAR 19: O16; SECOND YEAR 20: O16; SECOND YEAR 21: O16; SECOND YEAR 22: O16; SECOND YEAR 23: O16; SECOND YEAR 24: O16; THIRD YEAR 25: O16; THIRD YEAR 26: O16; THIRD YEAR 27: EN
89 | 31082732 | EE MENDES DE OLIVEIRA | SÃO JOÃO DO PARAÍSO | North | A1 | 1879 | 2066.9 | Internal | 8 | SECOND YEAR 17: PRO; SECOND YEAR 18: PRO; SECOND YEAR 19: PRO; SECOND YEAR 20: PO; SECOND YEAR 21: O17; SECOND YEAR 22: O17; SECOND YEAR 23: O17; SECOND YEAR 24: O17; THIRD YEAR 25: O17; THIRD YEAR 26: O17; THIRD YEAR 27: O17; THIRD YEAR 28: O17; THIRD YEAR 29: EN
73 | 31063452 | EE MARIA BATISTA CAVALCANTI | UBAÍ | North | A | 2313.1031 | 2544.4134 | Internal | 8 | SECOND YEAR 15: PRO; SECOND YEAR 16: PRO; SECOND YEAR 17: PRO; SECOND YEAR 18: PO; SECOND YEAR 19: O18; SECOND YEAR 20: O18; SECOND YEAR 21: O18; SECOND YEAR 22: O18; SECOND YEAR 23: O18; SECOND YEAR 24: O18; THIRD YEAR 25: O18; THIRD YEAR 26: O18; THIRD YEAR 27: EN
96 | 31079600 | EE SANTANA | BRASÍLIA DE MINAS | North | B | 2307 | 2537.7 | Internal | 8 | SECOND YEAR 17: PRO; SECOND YEAR 18: PRO; SECOND YEAR 19: PRO; SECOND YEAR 20: PO; SECOND YEAR 21: O19; SECOND YEAR 22: O19; SECOND YEAR 23: O19; SECOND YEAR 24: O19; THIRD YEAR 25: O19; THIRD YEAR 26: O19; THIRD YEAR 27: O19; THIRD YEAR 28: O19; THIRD YEAR 29: EN
75 | 31080349 | EE TIBURTINO PENA | FRANCISCO SÁ | North | D | 3084.16 | 3392.576 | Internal | 10 | SECOND YEAR 19: PRO; SECOND YEAR 20: PRO; SECOND YEAR 21: PRO; SECOND YEAR 22: PO; SECOND YEAR 23: O20; SECOND YEAR 24: O20; THIRD YEAR 25: O20; THIRD YEAR 26: O20; THIRD YEAR 27: O20; THIRD YEAR 28: O20; THIRD YEAR 29: O20; THIRD YEAR 30: O20; THIRD YEAR 31: O20; THIRD YEAR 32: O20; THIRD YEAR 33: EN
50 | 31034436 | EE JOAQUIM CORRÊA | JUATUBA | RMBH | A | 2060.4 | 2266.44 | Internal | 8 | THIRD YEAR 25: PRO; THIRD YEAR 26: PRO; THIRD YEAR 27: PRO; THIRD YEAR 28: PO; THIRD YEAR 29: O1; THIRD YEAR 30: O1; THIRD YEAR 31: O1; THIRD YEAR 32: O1; THIRD YEAR 33: O1; THIRD YEAR 34: O1; THIRD YEAR 35: O1; THIRD YEAR 36: O1; FOURTH YEAR 37: EN
10 | 31010430 | EE MARIA FLORIPES NASCIMENTO ALVES | SABARÁ | RMBH | B | 1945.27 | 2139.797 | Internal | 8 | THIRD YEAR 25: PRO; THIRD YEAR 26: PRO; THIRD YEAR 27: PRO; THIRD YEAR 28: PO; THIRD YEAR 29: O2; THIRD YEAR 30: O2; THIRD YEAR 31: O2; THIRD YEAR 32: O2; THIRD YEAR 33: O2; THIRD YEAR 34: O2; THIRD YEAR 35: O2; THIRD YEAR 36: O2; FOURTH YEAR 37: EN
109 | 31010421 | EE GENERAL CARNEIRO | SABARÁ | RMBH | B | 2168.76 | 2385.636 | Internal | 8 | SECOND YEAR 24: PRO; THIRD YEAR 25: PRO; THIRD YEAR 26: PRO; THIRD YEAR 27: PO; THIRD YEAR 28: O3; THIRD YEAR 29: O3; THIRD YEAR 30: O3; THIRD YEAR 31: O3; THIRD YEAR 32: O3; THIRD YEAR 33: O3; THIRD YEAR 34: O3; THIRD YEAR 35: O3; THIRD YEAR 36: EN
38 | 31008966 | EE SANTA QUITERIA | ESMERALDAS | RMBH | B | 2187.2 | 2405.92 | Internal | 8 | THIRD YEAR 25: PRO; THIRD YEAR 26: PRO; THIRD YEAR 27: PRO; THIRD YEAR 28: PO; THIRD YEAR 29: O4; THIRD YEAR 30: O4; THIRD YEAR 31: O4; THIRD YEAR 32: O4; THIRD YEAR 33: O4; THIRD YEAR 34: O4; THIRD YEAR 35: O4; THIRD YEAR 36: O4; FOURTH YEAR 37: EN
11 | 31008192 | EE PAULO NETO ALKIMIM | BRUMADINHO | RMBH | A | 2842.6 | 3126.86 | Internal | 10 | SECOND YEAR 22: PRO; SECOND YEAR 23: PRO; SECOND YEAR 24: PRO; THIRD YEAR 25: PO; THIRD YEAR 26: O5; THIRD YEAR 27: O5; THIRD YEAR 28: O5; THIRD YEAR 29: O5; THIRD YEAR 30: O5; THIRD YEAR 31: O5; THIRD YEAR 32: O5; THIRD YEAR 33: O5; THIRD YEAR 34: O5; THIRD YEAR 35: O5; THIRD YEAR 36: EN
5 | 31008141 | EE PAULINA ALUOTTO FERREIRA | BRUMADINHO | RMBH | B | 2232.79 | 2456.069 | Internal | 8 | SECOND YEAR 24: PRO; THIRD YEAR 25: PRO; THIRD YEAR 26: PRO; THIRD YEAR 27: PO; THIRD YEAR 28: O6; THIRD YEAR 29: O6; THIRD YEAR 30: O6; THIRD YEAR 31: O6; THIRD YEAR 32: O6; THIRD YEAR 33: O6; THIRD YEAR 34: O6; THIRD YEAR 35: O6; THIRD YEAR 36: EN
16 | 31351075 | EE ABELARDO DUARTE PASSOS | BRUMADINHO | RMBH | B | 1130.53 | 1243.583 | Internal | 8 | SECOND YEAR 24: PRO; THIRD YEAR 25: PRO; THIRD YEAR 26: PRO; THIRD YEAR 27: PO; THIRD YEAR 28: O7; THIRD YEAR 29: O7; THIRD YEAR 30: O7; THIRD YEAR 31: O7; THIRD YEAR 32: O7; THIRD YEAR 33: O7; THIRD YEAR 34: O7; THIRD YEAR 35: O7; THIRD YEAR 36: EN
27 | 31008737 | EE FRANCISCO FIRMO DE MATOS | CONTAGEM | RMBH | D | 3304.44 | 3634.884 | Internal | 10 | SECOND YEAR 22: PRO; SECOND YEAR 23: PRO; SECOND YEAR 24: PRO; THIRD YEAR 25: PO; THIRD YEAR 26: O8; THIRD YEAR 27: O8; THIRD YEAR 28: O8; THIRD YEAR 29: O8; THIRD YEAR 30: O8; THIRD YEAR 31: O8; THIRD YEAR 32: O8; THIRD YEAR 33: O8; THIRD YEAR 34: O8; THIRD YEAR 35: O8; THIRD YEAR 36: EN
51 | 31008753 | EE HELENA GUERRA | CONTAGEM | RMBH | D1 | 2445.18 | 2689.698 | Internal | 8 | SECOND YEAR 22: PRO; SECOND YEAR 23: PRO; SECOND YEAR 24: PRO; THIRD YEAR 25: PO; THIRD YEAR 26: O9; THIRD YEAR 27: O9; THIRD YEAR 28: O9; THIRD YEAR 29: O9; THIRD YEAR 30: O9; THIRD YEAR 31: O9; THIRD YEAR 32: O9; THIRD YEAR 33: O9; THIRD YEAR 34: EN
106 | 31000582 | EE PROFESSOR ALISSON PEREIRA GUIMARAES | BELO HORIZONTE | RMBH | D | 4926 | 5418.6 | Internal | 10 | THIRD YEAR 26: PRO; THIRD YEAR 27: PRO; THIRD YEAR 28: PRO; THIRD YEAR 29: PO; THIRD YEAR 30: O10; THIRD YEAR 31: O10; THIRD YEAR 32: O10; THIRD YEAR 33: O10; THIRD YEAR 34: O10; THIRD YEAR 35: O10; THIRD YEAR 36: O10; FOURTH YEAR 37: O10; FOURTH YEAR 38: O10; FOURTH YEAR 39: O10; FOURTH YEAR 40: EN
1 | 31000302 | EE PRESIDENTE DUTRA | BELO HORIZONTE | RMBH | D | 5113 | 5624.3 | Internal | 10 | THIRD YEAR 28: PRO; THIRD YEAR 29: PRO; THIRD YEAR 30: PRO; THIRD YEAR 31: PO; THIRD YEAR 32: O12; THIRD YEAR 33: O12; THIRD YEAR 34: O12; THIRD YEAR 35: O12; THIRD YEAR 36: O12; FOURTH YEAR 37: O12; FOURTH YEAR 38: O12; FOURTH YEAR 39: O12; FOURTH YEAR 40: O12; FOURTH YEAR 41: O12; FOURTH YEAR 42: EN
7 | 31342459 | EE PROFESSORA ALAIDE LISBOA DE OLIVEIRA | BELO HORIZONTE | RMBH | B | 2250.8428 | 2475.9271 | Internal | 8 | THIRD YEAR 26: PRO; THIRD YEAR 27: PRO; THIRD YEAR 28: PRO; THIRD YEAR 29: PO; THIRD YEAR 30: O15; THIRD YEAR 31: O15; THIRD YEAR 32: O15; THIRD YEAR 33: O15; THIRD YEAR 34: O15; THIRD YEAR 35: O15; THIRD YEAR 36: O15; FOURTH YEAR 37: O15; FOURTH YEAR 38: EN
29 | 31001201 | EE SILVIANO BRANDÃO | BELO HORIZONTE | RMBH | D | 2266.75 | 2493.425 | Internal | 8 | SECOND YEAR 24: PRO; THIRD YEAR 25: PRO; THIRD YEAR 26: PRO; THIRD YEAR 27: PO; THIRD YEAR 28: O17; THIRD YEAR 29: O17; THIRD YEAR 30: O17; THIRD YEAR 31: O17; THIRD YEAR 32: O17; THIRD YEAR 33: O17; THIRD YEAR 34: O17; THIRD YEAR 35: O17; THIRD YEAR 36: EN
44 | 31000159 | EE MANUEL CASASANTA | BELO HORIZONTE | RMBH | B | 1722.21 | 1894.431 | Internal | 8 | THIRD YEAR 26: PRO; THIRD YEAR 27: PRO; THIRD YEAR 28: PRO; THIRD YEAR 29: PO; THIRD YEAR 30: O11; THIRD YEAR 31: O11; THIRD YEAR 32: O11; THIRD YEAR 33: O11; THIRD YEAR 34: O11; THIRD YEAR 35: O11; THIRD YEAR 36: O11; FOURTH YEAR 37: O11; FOURTH YEAR 38: EN
21 | 31001805 | EE FLAVIO DOS SANTOS | BELO HORIZONTE | RMBH | D | 1821 | 2003.1 | Internal | 8 | THIRD YEAR 26: PRO; THIRD YEAR 27: PRO; THIRD YEAR 28: PRO; THIRD YEAR 29: PO; THIRD YEAR 30: O13; THIRD YEAR 31: O13; THIRD YEAR 32: O13; THIRD YEAR 33: O13; THIRD YEAR 34: O13; THIRD YEAR 35: O13; THIRD YEAR 36: O13; FOURTH YEAR 37: O13; FOURTH YEAR 38: EN
15 | 31000825 | EE ANA DE CARVALHO SILVEIRA | BELO HORIZONTE | RMBH | D | 1536 | 1689.6 | Internal | 8 | SECOND YEAR 22: PRO; SECOND YEAR 23: PRO; SECOND YEAR 24: PRO; THIRD YEAR 25: PO; THIRD YEAR 26: O18; THIRD YEAR 27: O18; THIRD YEAR 28: O18; THIRD YEAR 29: O18; THIRD YEAR 30: O18; THIRD YEAR 31: O18; THIRD YEAR 32: O18; THIRD YEAR 33: O18; THIRD YEAR 34: EN
112 | 31001333 | EE LAURA DAS CHAGAS FERREIRA | BELO HORIZONTE | RMBH | A | 1680.75 | 1848.825 | Internal | 8 | SECOND YEAR 24: PRO; THIRD YEAR 25: PRO; THIRD YEAR 26: PRO; THIRD YEAR 27: PO; THIRD YEAR 28: O19; THIRD YEAR 29: O19; THIRD YEAR 30: O19; THIRD YEAR 31: O19; THIRD YEAR 32: O19; THIRD YEAR 33: O19; THIRD YEAR 34: O19; THIRD YEAR 35: O19; THIRD YEAR 36: EN
115 | 31001074 | EE CELSO MACHADO | BELO HORIZONTE | RMBH | C | 6887.6886 | 7576.4575 | Internal | 10 | THIRD YEAR 28: PRO; THIRD YEAR 29: PRO; THIRD YEAR 30: PRO; THIRD YEAR 31: PO; THIRD YEAR 32: O20; THIRD YEAR 33: O20; THIRD YEAR 34: O20; THIRD YEAR 35: O20; THIRD YEAR 36: O20; FOURTH YEAR 37: O20; FOURTH YEAR 38: O20; FOURTH YEAR 39: O20; FOURTH YEAR 40: O20; FOURTH YEAR 41: O20; FOURTH YEAR 42: EN
4 | 31001783 | EE AUGUSTO DE LIMA (BELO HORIZONTE) | BELO HORIZONTE | RMBH | D1 | 1373 | 1510.3 | Internal | 8 | SECOND YEAR 22: PRO; SECOND YEAR 23: PRO; SECOND YEAR 24: PRO; THIRD YEAR 25: PO; THIRD YEAR 26: O16; THIRD YEAR 27: O16; THIRD YEAR 28: O16; THIRD YEAR 29: O16; THIRD YEAR 30: O16; THIRD YEAR 31: O16; THIRD YEAR 32: O16; THIRD YEAR 33: O16; THIRD YEAR 34: EN
6 | 31000493 | EE DEPUTADO ILACIR PEREIRA LIMA | BELO HORIZONTE | RMBH | C | 2731.23 | 3004.353 | Internal | 10 | THIRD YEAR 26: PRO; THIRD YEAR 27: PRO; THIRD YEAR 28: PRO; THIRD YEAR 29: PO; THIRD YEAR 30: O14; THIRD YEAR 31: O14; THIRD YEAR 32: O14; THIRD YEAR 33: O14; THIRD YEAR 34: O14; THIRD YEAR 35: O14; THIRD YEAR 36: O14; FOURTH YEAR 37: O14; FOURTH YEAR 38: O14; FOURTH YEAR 39: O14; FOURTH YEAR 40: EN
12 | 31001686 | EE WALT DISNEY | BELO HORIZONTE | RMBH | C | 3252.5682 | 3577.825 | Internal | 10 | THIRD YEAR 32: PRO; THIRD YEAR 33: PRO; THIRD YEAR 34: PRO; THIRD YEAR 35: PO; THIRD YEAR 36: O1; FOURTH YEAR 37: O1; FOURTH YEAR 38: O1; FOURTH YEAR 39: O1; FOURTH YEAR 40: O1; FOURTH YEAR 41: O1; FOURTH YEAR 42: O1; FOURTH YEAR 43: O1; FOURTH YEAR 44: O1; FOURTH YEAR 45: O1; FOURTH YEAR 46: EN
42 | 31000639 | EE MAURÍCIO MURGEL | BELO HORIZONTE | RMBH | D | 3921.0476 | 4313.1524 | Internal | 10 | THIRD YEAR 32: PRO; THIRD YEAR 33: PRO; THIRD YEAR 34: PRO; THIRD YEAR 35: PO; THIRD YEAR 36: O2; FOURTH YEAR 37: O2; FOURTH YEAR 38: O2; FOURTH YEAR 39: O2; FOURTH YEAR 40: O2; FOURTH YEAR 41: O2; FOURTH YEAR 42: O2; FOURTH YEAR 43: O2; FOURTH YEAR 44: O2; FOURTH YEAR 45: O2; FOURTH YEAR 46: EN
56 | 31009407 | EE NILO MAURICIO TRINDADE FIGUEIREDO | LAGOA SANTA | RMBH | A | 3188.9 | 3507.79 | Internal | 10 | THIRD YEAR 31: PRO; THIRD YEAR 32: PRO; THIRD YEAR 33: PRO; THIRD YEAR 34: PO; THIRD YEAR 35: O17; THIRD YEAR 36: O17; FOURTH YEAR 37: O17; FOURTH YEAR 38: O17; FOURTH YEAR 39: O17; FOURTH YEAR 40: O17; FOURTH YEAR 41: O17; FOURTH YEAR 42: O17; FOURTH YEAR 43: O17; FOURTH YEAR 44: O17; FOURTH YEAR 45: EN
57 | 31002488 | EE MANOEL FERNANDES DA SILVA (BELO HORIZONTE) EE DONATO WERNECK DE FREITAS. | BELO HORIZONTE | RMBH | B | 2598 | 2857.8 | Internal | 8 | THIRD YEAR 31: PRO; THIRD YEAR 32: PRO; THIRD YEAR 33: PRO; THIRD YEAR 34: PO; THIRD YEAR 35: O5; THIRD YEAR 36: O5; FOURTH YEAR 37: O5; FOURTH YEAR 38: O5; FOURTH YEAR 39: O5; FOURTH YEAR 40: O5; FOURTH YEAR 41: O5; FOURTH YEAR 42: O5; FOURTH YEAR 43: EN
53 | 31002500 | EE MARIA LUIZA MIRANDA BASTOS | BELO HORIZONTE | RMBH | D | 2843.25 | 3127.575 | Internal | 10 | THIRD YEAR 31: PRO; THIRD YEAR 32: PRO; THIRD YEAR 33: PRO; THIRD YEAR 34: PO; THIRD YEAR 35: O6; THIRD YEAR 36: O6; FOURTH YEAR 37: O6; FOURTH YEAR 38: O6; FOURTH YEAR 39: O6; FOURTH YEAR 40: O6; FOURTH YEAR 41: O6; FOURTH YEAR 42: O6; FOURTH YEAR 43: O6; FOURTH YEAR 44: O6; FOURTH YEAR 45: EN
37 | 31212601 | EE PROFESSOR OSVALDO FRANCO | BETIM | RMBH | A | 2755.91 | 3031.501 | Internal | 10 | THIRD YEAR 29: PRO; THIRD YEAR 30: PRO; THIRD YEAR 31: PRO; THIRD YEAR 32: PO; THIRD YEAR 33: O16; THIRD YEAR 34: O16; THIRD YEAR 35: O16; THIRD YEAR 36: O16; FOURTH YEAR 37: O16; FOURTH YEAR 38: O16; FOURTH YEAR 39: O16; FOURTH YEAR 40: O16; FOURTH YEAR 41: O16; FOURTH YEAR 42: O16; FOURTH YEAR 43: EN
25 | 31007927 | EE NOSSA SENHORA DO CARMO | BETIM | RMBH | B1 | 3028.57 | 3331.427 | Internal | 10 | THIRD YEAR 33: PRO; THIRD YEAR 34: PRO; THIRD YEAR 35: PRO; THIRD YEAR 36: PO; FOURTH YEAR 37: O11; FOURTH YEAR 38: O11; FOURTH YEAR 39: O11; FOURTH YEAR 40: O11; FOURTH YEAR 41: O11; FOURTH YEAR 42: O11; FOURTH YEAR 43: O11; FOURTH YEAR 44: O11; FOURTH YEAR 45: O11; FOURTH YEAR 46: O11; FOURTH YEAR 47: EN
28 | 31212598 | EE ANTÔNIO AUGUSTO RIBEIRO | BETIM | RMBH | A | 2500 | 2750 | Internal | 8 | THIRD YEAR 29: PRO; THIRD YEAR 30: PRO; THIRD YEAR 31: PRO; THIRD YEAR 32: PO; THIRD YEAR 33: O9; THIRD YEAR 34: O9; THIRD YEAR 35: O9; THIRD YEAR 36: O9; FOURTH YEAR 37: O9; FOURTH YEAR 38: O9; FOURTH YEAR 39: O9; FOURTH YEAR 40: O9; FOURTH YEAR 41: EN
41 | 31007994 | EE CECILIA MEIRELES | BETIM | RMBH | A | 2533.2 | 2786.52 | Internal | 8 | THIRD YEAR 31: PRO; THIRD YEAR 32: PRO; THIRD YEAR 33: PRO; THIRD YEAR 34: PO; THIRD YEAR 35: O7; THIRD YEAR 36: O7; FOURTH YEAR 37: O7; FOURTH YEAR 38: O7; FOURTH YEAR 39: O7; FOURTH YEAR 40: O7; FOURTH YEAR 41: O7; FOURTH YEAR 42: O7; FOURTH YEAR 43: EN
66 | 31062995 | EE ANTONIO ORTIGA | JUVENÍLIA | North | D1 | 3866.62 | 4253.282 | Internal | 10 | THIRD YEAR 31: PRO; THIRD YEAR 32: PRO; THIRD YEAR 33: PRO; THIRD YEAR 34: PO; THIRD YEAR 35: O8; THIRD YEAR 36: O8; FOURTH YEAR 37: O8; FOURTH YEAR 38: O8; FOURTH YEAR 39: O8; FOURTH YEAR 40: O8; FOURTH YEAR 41: O8; FOURTH YEAR 42: O8; FOURTH YEAR 43: O8; FOURTH YEAR 44: O8; FOURTH YEAR 45: EN
74 | 31246280 | EE MARIA ROSA NUNES (JANUÁRIA) | JANUÁRIA | North | A1 | 1415 | 1556.5 | Internal | 8 | THIRD YEAR 29: PRO; THIRD YEAR 30: PRO; THIRD YEAR 31: PRO; THIRD YEAR 32: PO; THIRD YEAR 33: O18; THIRD YEAR 34: O18; THIRD YEAR 35: O18; THIRD YEAR 36: O18; FOURTH YEAR 37: O18; FOURTH YEAR 38: O18; FOURTH YEAR 39: O18; FOURTH YEAR 40: O18; FOURTH YEAR 41: EN
74A | 31246280 | EE MARIA ROSA NUNES ANEXO (SÃO FRANCISCO) | SÃO FRANCISCO | North | A1 | 1265.26 | 1391.786 | Internal | 8 | THIRD YEAR 32: PRO; THIRD YEAR 33: PRO; THIRD YEAR 34: PRO; THIRD YEAR 35: PO; THIRD YEAR 36: O4; FOURTH YEAR 37: O4; FOURTH YEAR 38: O4; FOURTH YEAR 39: O4; FOURTH YEAR 40: O4; FOURTH YEAR 41: O4; FOURTH YEAR 42: O4; FOURTH YEAR 43: O4; FOURTH YEAR 44: EN
86 | 31081311 | EE BENJAMIN VERSIANI DOS ANJOS | MONTES CLAROS | North | B | 2090 | 2299 | Internal | 8 | THIRD YEAR 33: PRO; THIRD YEAR 34: PRO; THIRD YEAR 35: PRO; THIRD YEAR 36: PO; FOURTH YEAR 37: O13; FOURTH YEAR 38: O13; FOURTH YEAR 39: O13; FOURTH YEAR 40: O13; FOURTH YEAR 41: O13; FOURTH YEAR 42: O13; FOURTH YEAR 43: O13; FOURTH YEAR 44: O13; FOURTH YEAR 45: EN
80 | 31081761 | EE ANTONIO CANELA | MONTES CLAROS | North | D | 2734 | 3007.4 | Internal | 10 | THIRD YEAR 35: PRO; THIRD YEAR 36: PRO; FOURTH YEAR 37: PRO; FOURTH YEAR 38: PO; FOURTH YEAR 39: O10; FOURTH YEAR 40: O10; FOURTH YEAR 41: O10; FOURTH YEAR 42: O10; FOURTH YEAR 43: O10; FOURTH YEAR 44: O10; FOURTH YEAR 45: O10; FOURTH YEAR 46: O10; FOURTH YEAR 47: O10; FOURTH YEAR 48: O10; FIFTH YEAR 49: EN
94 | 31081507 | EE PROFESSOR HAMILTON LOPES | MONTES CLAROS | North | B | 2592 | 2851.2 | Internal | 8 | THIRD YEAR 31: PRO; THIRD YEAR 32: PRO; THIRD YEAR 33: PRO; THIRD YEAR 34: PO; THIRD YEAR 35: O3; THIRD YEAR 36: O3; FOURTH YEAR 37: O3; FOURTH YEAR 38: O3; FOURTH YEAR 39: O3; FOURTH YEAR 40: O3; FOURTH YEAR 41: O3; FOURTH YEAR 42: O3; FOURTH YEAR 43: EN